## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur - II | Midnapore Division | KUKRADA AND ITS ADJOINING MOUZAS PWSS | SM/14654 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 Cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,184 nos.) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Kukrada & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000459/2023-2024 | 5283/MD | 23/11/2023 | 21/05/2024 | CREATION CONSTRUCTION | 530.64 | 61.64 | 11.62 | 38
2 | PASCHIM MEDINIPUR | Kharagpur - II | Midnapore Division | KUKRADA AND ITS ADJOINING MOUZAS PWSS | SM/14654 | New | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 212/MD | 16/01/2023 |  | Resource Division | 42.05 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Kharagpur - II | Midnapore Mechanical | KUKRADA AND ITS ADJOINING MOUZAS PWSS | SM/14654 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUKRADA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001623/2022-2023 | 500/W/MMD | 20/03/2023 | 16/09/2023 | PADMA ENGINEERING CO. | 23 | 0 | 0 | 0
Total | [13 empty] | 595.7 | 61.64 | 10.35