## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona - II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1764 Nos.) under JJM with allied work for Hrisingpur PWSS in Chandrakona-II Block including supply of all labour & materials including 02 (Two) Year Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000678/2022-2023 | 816/MD | 21/03/2023 | 17/09/2023 | KHAN ENTERPRISE | 517.74 | 239.7 | 46.3 | 70
2 | PASCHIM MEDINIPUR | Chandrakona - II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 102/MD | 10/01/2023 |  | Resource Division | 32.36 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Chandrakona - II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 1373/MD | 02/05/2023 |  | Resource Division | 10.87 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona - II | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. |  |  | ORD/002037/2022-2023 | 945/W/MMD | 28/03/2023 | 24/09/2023 | DEBJYOTI BASU | 25.25 | 12.34 | 48.86 | 5
5 | PASCHIM MEDINIPUR | Chandrakona - II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | New service connection |  |  | BILL/00623/2023-2024 | 6/JMD | 11/10/2023 |  | WBSEDCL | 5.63 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona - II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | New service connection |  |  | BILL/00624/2023-2024 | 7/JMD | 11/10/2023 |  | WBSEDCL | 6.36 | 0 | 0 | 0
Total | [13 empty] | 598.21 | 252.03 | 42.13