## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15570 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (317) for Augmentation of Anandapur Sundarpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000179/2023-2024 | 2719/MD | 31/07/2023 | 29/09/2023 | MIDNAPUR PIPE CONCERN | 107.87 | 21.47 | 19.9 | 10
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15570 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000135/2022-2023 | 408/MD | 07/02/2023 |  | Resource Division | 2.72 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15570 | Augmentation | QUOTATION MONEY FOR ANANDAPUR WATER SUPPLY SCHEME, T W NO IV, [ AUGMENTATION ] , JJM WORKS, SCHEME CODE SM/15570, APPLICATION NO 2004815766, REFERENCE ID 204354166, GHATAL CCC, WBSEDCL |  |  | BILL/01677/2024-2025 | null | 22/07/2024 |  | WBSEDCL | 6.86 | 0 | 0 | null
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15570 | Augmentation | QUOTATION MONEY FOR ANANDAPUR- SUNDARPUR WATER SUPPLY SCHEME, T W NO IIII, [JOYNAGAR], AUGMENTATION, JJM WORKS, SCHEME CODE SM/15570, APPLICATION NO 2004815790, REFERENCE ID 204354167, GHATAL CCC, WBSEDCL |  |  | BILL/01678/2024-2025 | null | 22/07/2024 |  | WBSEDCL | 3.4 | 0 | 0 | null
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15570 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002015/2022-2023 | 913/W/MMD | 27/03/2023 | 23/09/2023 | GLACIER ENGINEERING CO. | 25.26 | 8.84 | 34.99 | 60
Total | [13 empty] | 146.12 | 30.31 | 20.74