## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | DUAN-II AND ITS ADJOINING MOUJAS PWSS | SM/17616 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House, Boundary Wall, laying of Rising Main & Providing Functional Household Tap Connection (4740 Nos) including 2 years Operation & Maintenance For Dingal, Duan and Gobindapur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000211/2023-2024 | 2826/MD | 07/08/2023 | 04/03/2024 | GOBINDA MAITY | 1375.06 | 0 | 0 | 74
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | DUAN-II AND ITS ADJOINING MOUJAS PWSS | SM/17616 | New | Material Requisition To Resource Division |  |  | RTOR000231/2023-2024 | 1519/MD | 12/05/2023 |  | Resource Division | 24.68 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | DUAN-II AND ITS ADJOINING MOUJAS PWSS | SM/17616 | New | Electrict quotation bill for TW-II of DUAN-II pwss (Ref Consumar ID-204235945),Application No-2004627252,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. |  |  | BILL/04396/2023-2024 | BP-2023-24-816 | 13/03/2024 |  | WBSEDCL | 3.26 | 0 | 0 | null
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | DUAN-II AND ITS ADJOINING MOUJAS PWSS | SM/17616 | New | Electrict quotation bill for TW-I of DUAN-II pwss (Ref Consumar ID-204235948),Application No-2004627235,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. |  |  | BILL/04397/2023-2024 | BP-2023-24-815 | 13/03/2024 |  | WBSEDCL | 3.36 | 0 | 0 | null
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | DUAN-II AND ITS ADJOINING MOUJAS PWSS | SM/17616 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DUAN-II AND ITS ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002201/2022-2023 | 477/W/MMD | 20/03/2023 | 16/09/2023 | M/S. SAJAHAN CHOWDHURY | 23 | 0 | 0 | 60
Total | [13 empty] | 1429.36 | 0 | 0