## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona - I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/18032 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House , Boundary Wall soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1990 Nos.) under JJM with allied work for Mahespur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000060/2023-2024 | 2418/MD | 13/07/2023 | 09/01/2024 | DULAL CHANDRA DAS | 609.59 | 0 | 0 | 47
2 | PASCHIM MEDINIPUR | Chandrakona - I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/18032 | New | Laying of Rising main & interconnection for Maheshpur & its adjoining mouzas PWSS, Block: - Chandrakona-I, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000473/2024-2025 | 459/MD | 11/02/2025 | 28/03/2025 | DULAL CHANDRA DAS | 10.5 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Chandrakona - I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/18032 | New | Installation of Display Board for JJM work at different Piped Water Supply Scheme under different block within Midnapore Division, PHE Dte. [PART-A] | Assistant Engineer (HQ) |  | ORD/000784/2023-2024 | 506/MD | 27/02/2024 | 08/03/2024 | PULLOCK KUMAR GHOSH | 0.96 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Chandrakona - I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/18032 | New | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 72/MD | 09/01/2023 | 09/01/2023 | Resource Division | 34.76 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona - I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/18032 | New | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 1508/MD | 12/05/2023 | 12/05/2023 | Resource Division | 12.26 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona - I | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/18032 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002205/2022-2023 | 581/W/MMD | 20/03/2023 | 16/09/2023 | B.P.TRADING CORPORATION | 25.26 | 0 | 0 | 90
7 | PASCHIM MEDINIPUR | Chandrakona - I | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/18032 | New | Quotaton for new service connection charges for Maheshpur tw-II water supply scheme. |  |  | BILL/00813/2024-2025 | 295/JMD | 09/08/2024 | 09/08/2024 | WBSEDCL | 3.48 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Chandrakona - I | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TOACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/18032 | New | New Service connection charges. |  |  | BILL/01251/2023-2024 | 49/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 4.07 | 0 | 0 | 0
Total | [13 empty] | 700.89 | 0 | 0