## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Tamluk District Hospital water supply scheme under MMD PHE Dte. |  |  | ORD/000039/2021-2022 | 598/HESD | 26/05/2021 | 05/06/2021 | BHABANI PRASAD MANNA | 2.26 | 1.35 | 59.91 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Contai S.A. Rej. Zone-I water supply scheme under MMD PHE Dte. |  |  | ORD/000042/2021-2022 | 600/HESD | 26/05/2021 | 15/06/2021 | P.K.ENGINEERING | 2.76 | 2.06 | 74.43 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Baghaput water supply scheme under MMD PHE Dte. |  |  | ORD/000045/2021-2022 | 602/HESD | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 1.38 | 0.96 | 69.01 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Digha S.G. Hospital water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000048/2021-2022 | 592/HESD | 26/05/2021 | 05/06/2021 | PRANAB KUMAR DAS | 2.09 | 1.18 | 56.26 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Haipur water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000049/2021-2022 | 599/HESD | 26/05/2021 | 05/06/2021 | PRANAB KUMAR DAS | 1.26 | 0.87 | 69.39 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Contai S.A. Rej. Zone-II water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000051/2021-2022 | 597/HESD | 26/05/2021 | 05/06/2021 | P.K.ENGINEERING | 1.34 | 1.15 | 85.6 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Contai S.A. Rej. Zone-III water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000052/2021-2022 | 601/HESD | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 1.84 | 1.49 | 81.24 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Anurai water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000054/2021-2022 | 603/HESD | 26/05/2021 | 05/06/2021 | P.K.ENGINEERING | 1.3 | 1.27 | 98.04 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Baharchand Beria water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000055/2021-2022 | 596/HESD | 26/05/2021 | 05/06/2021 | P.K.ENGINEERING | 1.3 | 1.28 | 98.69 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Basudev Beria water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000056/2021-2022 | 590/HESD | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 1.47 | 1.25 | 85.27 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Bankiput water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000057/2021-2022 | 604/HESD | 26/05/2021 | 15/06/2021 | SUBHASIS ROY | 2.43 | 2.4 | 98.95 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Dariapur water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000058/2021-2022 | 605/HESD | 26/05/2021 | 05/06/2021 | M/S EMMESS | 1.17 | 0.79 | 67.54 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Contai S.A. Rej. Zone-IV water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000059/2021-2022 | 651/HESD | 26/05/2021 | 05/06/2021 | PRANAB KUMAR DAS | 2.6 | 1.06 | 40.72 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Talda water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000060/2021-2022 | 652/HESD | 26/05/2021 | 05/06/2021 | S.S.GHORAI | 1.26 | 1.17 | 93.25 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Murisai water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000061/2021-2022 | 594/HESD | 26/05/2021 | 05/06/2021 | P.K.ENGINEERING | 1.17 | 1.14 | 97.1 | 0
16 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Sankarpur water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000062/2021-2022 | 606/HESD | 26/05/2021 | 05/06/2021 | PRANAB KUMAR DAS | 1.26 | 0.81 | 64.67 | 0
17 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Durmut water supply scheme under MMD PHE Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000063/2021-2022 | 607/HESD | 26/05/2021 | 05/06/2021 | PRANAB KUMAR DAS | 1.34 | 1.22 | 90.65 | 0
18 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Bajkul Zone-I water supply scheme under MMD PHE Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000064/2021-2022 | 608/HESD | 26/05/2021 | 05/06/2021 | ECO ENTERPRISE | 1.17 | 0.8 | 68.62 | 0
19 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Sherkhanchak water supply scheme under MMD PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000065/2021-2022 | 609/HESD | 26/05/2021 | 15/06/2021 | SUBHASIS ROY | 4.27 | 2.55 | 59.72 | 0
20 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Supply, delivery of fuel for delpt. Diesel Generating set & allied works on the situation of "Yaas" 2021 at Nijkasba water supply scheme under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000066/2021-2022 | 587/HESD | 26/05/2021 | 05/06/2021 | PRANAB KUMAR DAS | 0.2 | 0.11 | 56.52 | 0
21 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Argoal water supply scheme under MMD PHE Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000067/2021-2022 | 611/HESD | 26/05/2021 | 05/06/2021 | PRANAB KUMAR DAS | 1.26 | 0.7 | 55.7 | 0
22 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Bagmari water supply scheme under MMD PHE Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000068/2021-2022 | 612/HESD | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 1.92 | 1.3 | 67.67 | 0
23 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Tamalda water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000069/2021-2022 | 613/HESD | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 1.26 | 1.21 | 95.95 | 0
24 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Digha East Zone water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000070/2021-2022 | 615/HESD | 26/05/2021 | 05/06/2021 | PRANAB KUMAR DAS | 1.3 | 0.98 | 75.47 | 0
25 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Digha West Zone water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000071/2021-2022 | 616/HESD | 26/05/2021 | 05/06/2021 | S.S.GHORAI | 1.17 | 0.78 | 66.45 | 0
26 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Low lift pumping station of Digha Central Zone water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000072/2021-2022 | 653/HESD | 26/05/2021 | 05/06/2021 | S.S.GHORAI | 1.17 | 0.56 | 47.95 | 0
27 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Badhia water supply scheme under MMD PHE Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2021-2022 | 618/HESD | 26/05/2021 | 05/06/2021 | PRANAB KUMAR DAS | 2.92 | 1.73 | 59.28 | 0
28 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Sankarpur (Ramnagar-II) water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000074/2021-2022 | 586/HESD | 26/05/2021 | 15/06/2021 | PRANAB KUMAR DAS | 2.6 | 2.22 | 85.51 | 0
29 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Kanpur water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000075/2021-2022 | 621/HESD | 26/05/2021 | 05/06/2021 | S.S.GHORAI | 1.26 | 0.85 | 67.7 | 0
30 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Mandarmoni water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000076/2021-2022 | 622/HESD | 26/05/2021 | 15/06/2021 | S.S.GHORAI | 2.26 | 1.42 | 62.89 | 0
31 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Chapbosan water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000077/2021-2022 | 623/HESD | 26/05/2021 | 05/06/2021 | SHOVAN KUMAR DAS | 2.26 | 1.48 | 65.53 | 0
32 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Anantapur Zone-I water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000078/2021-2022 | 624/HESD | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 2.01 | 1.18 | 59.05 | 0
33 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Anantapur Zone-II water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000079/2021-2022 | 625/HESD | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 2.01 | 1.12 | 55.67 | 0
34 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Bargodagodar water supply scheme under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000080/2021-2022 | 633/HESD | 26/05/2021 | 05/06/2021 | SHOVAN KUMAR DAS | 2.26 | 1.44 | 63.65 | 0
35 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Natshalakshya Zone-I water supply scheme under MMD PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000081/2021-2022 | 638/HESD | 26/05/2021 | 05/06/2021 | M/S B.M. ELECTRICAL | 2.26 | 1.35 | 59.91 | 0
36 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Natshalakshya Zone-II water supply scheme under MMD PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000082/2021-2022 | 654/HESD | 26/05/2021 | 05/06/2021 | M/S B.M. ELECTRICAL | 1.92 | 1.23 | 63.86 | 0
37 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Khejuri water supply scheme under MMD PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000083/2021-2022 | 591/HESD | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 1.34 | 1.34 | 100 | 0
38 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Kanakpur water supply scheme under MMD PHE Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000084/2021-2022 | 610/HESD | 26/05/2021 | 05/06/2021 | M/S EMMESS | 1.17 | 1.01 | 86.4 | 0
39 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Paniparul water supply scheme under MMD PHE Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000085/2021-2022 | 614/HESD | 26/05/2021 | 05/06/2021 | M/S EMMESS | 1.26 | 0.95 | 75.32 | 0
40 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Chirulia water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000086/2021-2022 | 585/HESD | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 1.38 | 1.01 | 72.99 | 0
41 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at High lift pumping station of Digha Central Zone water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000087/2021-2022 | 617/HESD | 26/05/2021 | 05/06/2021 | MENAKA ENTERPRISE | 3.13 | 1.44 | 45.88 | 0
42 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Chandanpur water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000088/2021-2022 | 619/HESD | 26/05/2021 | 05/06/2021 | MENAKA ENTERPRISE | 1.26 | 0.93 | 73.63 | 0
43 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Ranisai water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000089/2021-2022 | 620/HESD | 26/05/2021 | 05/06/2021 | MENAKA ENTERPRISE | 4.84 | 3.42 | 70.54 | 0
44 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 for unintrupted power supply at Digha S.G. Hospital under MMD, PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000090/2021-2022 | 595/HESD | 26/05/2021 | 05/06/2021 | MENAKA ENTERPRISE | 1.17 | 0.92 | 78.6 | 0
45 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 for Ramnagar MTU under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000091/2021-2022 | 593/HESD | 26/05/2021 | 05/06/2021 | MENAKA ENTERPRISE | 1.17 | 0.96 | 82.06 | 0
46 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Mahisda Zone-I water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000093/2021-2022 | 589/HESD | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 1.92 | 1.27 | 66.07 | 0
47 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Mahisda Zone-II water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000094/2021-2022 | 627/HESD | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 1.26 | 0.81 | 64.67 | 65
48 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Hour water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000095/2021-2022 | 628/HESD | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 2.09 | 1.35 | 64.77 | 0
49 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Gobindanagar Zone-I water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000096/2021-2022 | 588/HESD | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 2.26 | 1.31 | 58.03 | 0
50 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Purba Bakulda water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000097/2021-2022 | 629/HESD | 26/05/2021 | 05/06/2021 | SUJOY RANJAN BHOWMICK | 2.26 | 1.17 | 51.65 | 0
51 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Thenkuachak Zone-I water supply scheme under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000102/2021-2022 | 635/HESD | 26/05/2021 | 05/06/2021 | BHABANI PRASAD MANNA | 1.92 | 1.27 | 66.34 | 0
52 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Thenkuachak Zone-II water supply scheme under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000103/2021-2022 | 636/HESD | 26/05/2021 | 05/06/2021 | BHABANI PRASAD MANNA | 1.92 | 1.28 | 66.78 | 0
53 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Habicak water supply scheme under MMD PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000104/2021-2022 | 637/HESD | 26/05/2021 | 05/06/2021 | M/S EMMESS | 2.26 | 1.44 | 63.66 | 0
54 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Batkundu water supply scheme under MMD PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000105/2021-2022 | 639/HESD | 26/05/2021 | 05/06/2021 | M/S B.M. ELECTRICAL | 1.92 | 1.18 | 61.65 | 0
55 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Chaitanyapur Zone-I water supply scheme under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000106/2021-2022 | 640/HESD | 26/05/2021 | 05/06/2021 | M/S B.M. ELECTRICAL | 3.26 | 2.08 | 63.81 | 0
56 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Chaitanyapur Zone-II water supply scheme under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000107/2021-2022 | 641/HESD | 26/05/2021 | 05/06/2021 | M/S B.M. ELECTRICAL | 1.92 | 1.14 | 59.45 | 0
57 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Barsundra water supply scheme under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000108/2021-2022 | 642/HESD | 26/05/2021 | 05/06/2021 | BHABANI PRASAD MANNA | 1.92 | 1.12 | 58.12 | 0
58 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Dariberia water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000109/2021-2022 | 643/HESD | 26/05/2021 | 05/06/2021 | SUJOY RANJAN BHOWMICK | 1.92 | 1.23 | 63.86 | 0
59 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Gholpukuria Zone-I water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000110/2021-2022 | 644/HESD | 26/05/2021 | 05/06/2021 | M/S EMMESS | 2.26 | 1.44 | 63.66 | 0
60 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Gholpukuria Zone-II water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000111/2021-2022 | 645/HESD | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 2.26 | 1.52 | 67.41 | 0
61 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Dakshin Mechogram water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000113/2021-2022 | 647/HESD | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 2.09 | 1.16 | 55.64 | 0
62 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Nimtouri Administrative Building water supply scheme under MMD PHE Dte. |  | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000114/2021-2022 | 648/HESD | 26/05/2021 | 05/06/2021 | SUJOY RANJAN BHOWMICK | 2.26 | 1.17 | 51.65 | 0
63 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Supply of gunny bag, nylone rope and Packing of water pouches at Ramnagar Office Campus for preparedness of super cyclonic storm Yaas, MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000115/2021-2022 | 649/HESD | 26/05/2021 | 05/06/2021 | MENAKA ENTERPRISE | 1.61 | 1.59 | 99.07 | 0
64 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Supply of gunny bag, nylone rope and Packing of water pouches at Natshalakshya Head works site for preparedness of super cyclonic storm Yaas, MMD PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000116/2021-2022 | 650/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 3.56 | 3.56 | 100 | 0
65 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Supply of gunny bag, nylone rope and Packing of water pouches at MTU Sherkhan Chak, Dist. Purba Midnapore for preparedness of super cyclonic storm Yaas, MMD PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000121/2021-2022 | 702/HESD | 02/06/2021 | 09/06/2021 | MENAKA ENTERPRISE | 0.39 | 0.39 | 100 | 0
66 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Ghatal SD Hospital water supply scheme under MMD PHE Dte. |  |  | ORD/000124/2021-2022 | 630/MMSD-I | 26/05/2021 | 05/06/2021 | ECO ENTERPRISE | 1.69 | 1.17 | 69.08 | 0
67 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Digri TB Hospital water supply scheme under MMD PHE Dte. |  |  | ORD/000125/2021-2022 | 631/MMSD-I | 26/05/2021 | 05/06/2021 | M/S EMMESS | 1.69 | 1.45 | 85.64 | 0
68 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Medinipur Medical College & Hospital water supply scheme under MMD PHE Dte. |  |  | ORD/000126/2021-2022 | 632/MMSD-I | 26/05/2021 | 05/06/2021 | P.K.ENGINEERING | 2.05 | 1.33 | 64.87 | 0
69 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Kharagpur S.D. Hospital water supply scheme under MMD PHE Dte. |  |  | ORD/000127/2021-2022 | 633/MMSD-I | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 2.05 | 1.31 | 63.9 | 0
70 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Choto Khelna water supply scheme under MMD PHE Dte. |  |  | ORD/000128/2021-2022 | 634/MMSD-I | 26/05/2021 | 05/06/2021 | SUBHASIS ROY | 1.49 | 1.22 | 81.78 | 0
71 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Jamna water supply scheme under MMD PHE Dte. |  |  | ORD/000129/2021-2022 | 635/MMSD-I | 26/05/2021 | 05/06/2021 | M/S EMMESS | 1.49 | 1.44 | 96.58 | 0
72 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Belun water supply scheme under MMD PHE Dte. |  |  | ORD/000130/2021-2022 | 636/MMSD-I | 26/05/2021 | 05/06/2021 | M/S EMMESS | 1.49 | 1.42 | 95.45 | 0
73 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Bhemwa water supply scheme under MMD PHE Dte. |  |  | ORD/000131/2021-2022 | 637/MMSD-I | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 1.81 | 1.62 | 89.98 | 0
74 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Bishnupur water supply scheme under MMD PHE Dte. |  |  | ORD/000132/2021-2022 | 638/MMSD-I | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 2.47 | 1.83 | 74.2 | 0
75 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Chandkuri water supply scheme under MMD PHE Dte. |  |  | ORD/000133/2021-2022 | 639/MMSD-I | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 1.81 | 1.51 | 83.71 | 0
76 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Bural water supply scheme under MMD PHE Dte. |  |  | ORD/000134/2021-2022 | 640/MMSD-I | 26/05/2021 | 05/06/2021 | P.K.ENGINEERING | 1.81 | 1.47 | 81.52 | 0
77 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Lutunia water supply scheme under MMD PHE Dte. |  |  | ORD/000135/2021-2022 | 641/MMSD-I | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 1.81 | 1.62 | 89.98 | 0
78 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Vikini Nischintapur water supply scheme under MMD PHE Dte. |  |  | ORD/000136/2021-2022 | 642/MMSD-I | 26/05/2021 | 05/06/2021 | P.K.ENGINEERING | 1.81 | 1.44 | 79.95 | 0
79 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Kolanda water supply scheme under MMD PHE Dte. |  |  | ORD/000137/2021-2022 | 643/MMSD-I | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 1.81 | 1.62 | 89.98 | 0
80 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Sabang water supply scheme under MMD PHE Dte. |  |  | ORD/000138/2021-2022 | 644/MMSD-I | 26/05/2021 | 05/06/2021 | DEBJYOTI BASU | 1.81 | 1.51 | 83.71 | 0
81 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Raghunathchak water supply scheme under MMD PHE Dte. |  |  | ORD/000139/2021-2022 | 645/MMSD-I | 26/05/2021 | 05/06/2021 | M/S EMMESS | 1.49 | 1.44 | 96.58 | 0
82 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Garhbeta water supply scheme under MMD PHE Dte. |  |  | ORD/000141/2021-2022 | 646/MMSD-I | 26/05/2021 | 05/06/2021 | P.K.ENGINEERING | 1.81 | 1.51 | 83.71 | 0
83 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Supply of gunny bag, nylone rope and Packing of water pouches at MMSD1 Campus for preparedness of super cyclonic storm Yaas, MMD PHE Dte. |  |  | ORD/000142/2021-2022 | 647/MMSD-I | 26/05/2021 | 05/06/2021 | RITESH ENTERPRISE | 1.01 | 1.01 | 100 | 0
84 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Mahammadpur water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000143/2021-2022 | 659/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 1.92 | 1.22 | 63.42 | 0
85 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Jalpai Part-II water supply scheme under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000144/2021-2022 | 658/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 1.92 | 1.27 | 66.07 | 0
86 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Sonachura water supply scheme under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000145/2021-2022 | 657/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 2.26 | 1.27 | 56.16 | 0
87 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Manikpur water supply scheme under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000147/2021-2022 | 656/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 1.92 | 1.27 | 66.07 | 0
88 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Tajpur water supply scheme under MMD PHE Dte. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000148/2021-2022 | 655/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 1.92 | 1.23 | 63.86 | 0
89 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary water supply arrangement by hiring vehicle due to ¿YAAS¿ affected areas under Ramnagar-I block in the dict. of Purba Medinipur under MMD, PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000154/2021-2022 | 681/HESD | 28/05/2021 | 17/07/2021 | P.K.ENGINEERING | 2.32 | 0.83 | 35.66 | 0
90 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary water supply arrangement by hiring vehicle due to ¿YAAS¿ affected areas under Ramnagar-II block in the dict. of Purba Medinipur under MMD, PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000156/2021-2022 | 680/HESD | 28/05/2021 | 17/08/2021 | MENAKA ENTERPRISE | 4.51 | 4.51 | 100 | 0
91 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary water supply arrangement by hiring vehicle due to ¿YAAS¿ affected areas under Contai-I block in the dict. of Purba Medinipur under MMD, PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000157/2021-2022 | 682/HESD | 28/05/2021 | 17/07/2021 | S.S.GHORAI | 2.32 | 1.06 | 45.6 | 0
92 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary water supply arrangement by hiring vehicle due to ¿YAAS¿ affected areas under Contai-II block in the dict. of Purba Medinipur under MMD, PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000158/2021-2022 | 685/HESD | 28/05/2021 | 08/08/2021 | DIPALI CONSTRUCTION | 3.7 | 2.84 | 76.9 | 0
93 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary water supply arrangement by hiring vehicle due to ¿YAAS¿ affected areas under Khejuri-II block in the dict. of Purba Medinipur under MMD, PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000159/2021-2022 | 684/HESD | 28/05/2021 | 28/08/2021 | SUBHASIS ROY | 4.31 | 1.34 | 31.06 | 0
94 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Sankarpur TW-II water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000160/2021-2022 | 703/HESD | 02/06/2021 | 12/06/2021 | DIPALI CONSTRUCTION | 2.06 | 1.76 | 85.39 | 0
95 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary water supply arrangement by hiring vehicle due to ¿YAAS¿ affected areas under Chandipur block in the dict. of Purba Medinipur under MMD, PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000161/2021-2022 | 683/HESD | 28/05/2021 | 17/07/2021 | SOUMEN ELECTRIC | 2.32 | 1.41 | 60.78 | 0
96 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Contai S.D. Hospital water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000162/2021-2022 | 665/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 2.26 | 1.92 | 85.14 | 0
97 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Contai State Welfare water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000163/2021-2022 | 664/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 1.58 | 1.22 | 76.82 | 0
98 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Kumirda water supply scheme under MMD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000164/2021-2022 | 661/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 1.84 | 1.32 | 71.72 | 0
99 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Bhagwanpur Zone-I water supply scheme under MMD PHE Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000165/2021-2022 | 663/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 1.75 | 1.32 | 75.19 | 0
100 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Dhanyaghara water supply scheme under MMD PHE Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000166/2021-2022 | 662/HESD | 26/05/2021 | 05/06/2021 | SOUMEN ELECTRIC | 2.09 | 1.52 | 72.73 | 0
101 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Continuation order for emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Anurai water supply scheme under MMD, PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000174/2021-2022 | 704/HESD | 02/06/2021 | 12/06/2021 | P.K.ENGINEERING | 1.3 | 0.6 | 45.86 | 0
102 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Continuation order for emergency hiring charges of Diesel Generating set on the situation of "Yaas" 2021 at Khejuri water supply scheme under MMD PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000176/2021-2022 | 716/HESD | 03/06/2021 | 13/06/2021 | SUBHASIS ROY | 1.34 | 0 | 0 | 0
103 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Running repairing & restoration work of MTU located in Ramnagar & Natshalakshya W/S Scheme due to super cyclone ¿YAAS¿ 2021 in Purba Medinipur dist. under MMD, PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000282/2021-2022 | 708/HESD | 02/06/2021 | 09/06/2021 | ALOK ENTERPRISE | 2.94 | 2.94 | 100 | 0
104 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Repairing, Restoration work of disinfecting arrangement and other electrical/ mechanical accessoires along with supply of disinfectant due to Yaas affected areas of block Ramnagar I & Ramnagar II Dist. Purba Midnapore under HESD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000286/2021-2022 | 720/HESD | 04/06/2021 | 11/06/2021 | S.S.GHORAI | 2.86 | 2.53 | 88.62 | 0
105 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary Water Supply through departmental water tankers WB-89-2311 from DCC campus to different Super Cyclone Yaas affected area in the Dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000287/2021-2022 | 686/HESD | 28/05/2021 | 04/06/2021 | SUJOY RANJAN BHOWMICK | 2.19 | 0.89 | 40.43 | 0
106 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Repairing,restoration work of disinfecting arrangement and other electrical / mechanical accessories along with supply of disinfection due to YAAS effected areas of block Egra I & Egra II Dist. Purba Midnapore under HESD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000288/2021-2022 | 721/HESD | 04/06/2021 | 11/06/2021 | MENAKA ENTERPRISE | 2.57 | 2.55 | 99.18 | 0
107 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Repairing , restoration work of disinfecting arrangement and other electrical / mechanical accessories along with supply of disinfectant due to YAAS effected areas of block Khejuri I & Khejuri II Dist. Purba Midnapore under HESD PHE Dte. |  | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000289/2021-2022 | 722/HESD | 04/06/2021 | 11/06/2021 | SUBHASIS ROY | 1.16 | 1.16 | 100 | 0
108 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Repairing, Restoration work of disinfecting arrangement and other electrical/ mechanical accessoires along with supply of disinfectant due to Yaas affected areas of block Contai I , Contai II , Contai III Dist. Purba Midnapore under HESD PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000290/2021-2022 | 723/HESD | 04/06/2021 | 11/06/2021 | SOUMEN ELECTRIC | 4.85 | 4.84 | 99.85 | 0
109 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Continuation work order for temporary water supply arrangement by hiring vehicle due to ¿YAAS¿ affected areas under Contai-II block in the dict. of Purba Medinipur under MMD, PHE Dte. |  | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000296/2021-2022 | 736/HESD | 07/06/2021 | 14/06/2021 | DIPALI CONSTRUCTION | 3.7 | 0.64 | 17.26 | 0
110 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Supply of different MTU spares for preparedness of super cyclonic storm Yaas at MMSD-1, under MMD PHE Dte. |  |  | ORD/000298/2021-2022 | 650/MMSD-I | 26/05/2021 | 02/06/2021 | ALOK ENTERPRISE | 4.28 | 0 | 0 | 0
111 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Chandalbandh water supply scheme, Gopiballavpur-I Block under JMD PHE Dte. |  |  | ORD/000305/2021-2022 | 655/MMSD-I | 26/05/2021 | 02/06/2021 | SUBHASIS ROY | 0.79 | 0.56 | 71.51 | 0
112 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Chatinasole water supply scheme under JMD PHE Dte. |  |  | ORD/000306/2021-2022 | 654/MMSD-I | 26/05/2021 | 02/06/2021 | SUBHASIS ROY | 0.79 | 0.56 | 71.51 | 0
113 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Dahamunda water supply scheme, Gopiballavpur-I Block under JMD PHE Dte. |  |  | ORD/000307/2021-2022 | 653/MMSD-I | 26/05/2021 | 02/06/2021 | SUBHASIS ROY | 0.79 | 0.64 | 81.87 | 0
114 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of "YAAS" 2021 at Kultikri water supply scheme, Sankrail Block under JMD PHE Dte. |  |  | ORD/000308/2021-2022 | 659/MMSD-I | 26/05/2021 | 02/06/2021 | M/S EMMESS | 0.79 | 0.68 | 87.05 | 0
115 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Repairing and restoration work for different mechanicl - electrical equipments at Digha Banglow due to super cyclone storm YAAS under HESD under Midnapore Mechanical Division, P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000899/2021-2022 | 2048/W/MMD | 22/09/2021 | 29/09/2021 | MENAKA ENTERPRISE | 2.67 | 1.91 | 71.8 | 0
116 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Transportation of water pouches from MMSD-I Campus to HESD office campus by hiring vehicle due to YAAS super cyclone under Midnapore Mechanical Division, P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I |  | ORD/000900/2021-2022 | 2049/W/MMD | 22/09/2021 | 29/09/2021 | SUBHASIS ROY | 0.93 | 0.93 | 100 | 0
117 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Transportation of water pouches from DCC Campus to MMSD-I office campus by hiring vehicle due to YAAS super cyclone under Midnapore Mechanical Division, P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I |  | ORD/000901/2021-2022 | 2051/W/MMD | 22/09/2021 | 29/09/2021 | SUBHASIS ROY | 0.35 | 0.35 | 100 | 0
118 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Repairing and renovation of Existing M.TU under Dist. Purba Midnapore (Tamluk) under Medinipur Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000951/2021-2022 | 2141/W/MMD | 04/10/2021 | 24/10/2021 | ALOK ENTERPRISE | 21.55 | 21.55 | 100 | 0
119 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Transportation of water pouches from MMSD-I Campus to Ramnagar office campus by hiring vehicle due to YAAS super cyclone under Midnapore Mechanical Division, P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000958/2021-2022 | 2050/W/MMD | 22/09/2021 | 29/09/2021 | SUBHASIS ROY | 1.51 | 1.34 | 88.46 | 0
120 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary water supply arrangement by hiring vehicles from DCC Campus to different Super Cyclone Yaas affected areas under JMD PHE Dte. |  |  | ORD/001100/2021-2022 | 661/MMSD-I | 26/05/2021 | 10/06/2021 | DEBJYOTI BASU | 1.56 | 1.18 | 75.62 | 0
121 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary water supply arrangement through departmental water tankers WB 89 2320 & WB 89 2322 from DCC Campus to different Super Cyclone Yaas affected areas under JMD PHE Dte. |  |  | ORD/001101/2021-2022 | 662/MMSD-I | 26/05/2021 | 10/06/2021 | SUJOY RANJAN BHOWMICK | 1.56 | 0.97 | 62.46 | 0
122 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Continuation order for emergency hiring charges of Diesel Generating set on the situation of 'Yaas' 2021 at Khejuri water supply scheme under MMD PHE Dte. |  |  | VCH/004649/2021-2022 | BP-2021-22-44 | 05/01/2022 |  | SUBHASIS ROY | 0.58 | 0 | 0 | 0
123 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary water supply arrangement by hiring vehicles from DCC Campus to different Super Cyclone Yaas affected areas under JMD PHE Dte. |  |  | VCH/005385/2021-2022 | null | 03/03/2022 |  | DEBJYOTI BASU | 1.18 | 0 | 0 | 0
124 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Temporary water supply arrangement through departmental water tankers WB 89 2320 & WB 89 2322 from DCC Campus to different Super Cyclone Yaas affected areas under JMD PHE Dte. |  |  | VCH/005386/2021-2022 | null | 03/03/2022 |  | SUJOY RANJAN BHOWMICK | 0.97 | 0 | 0 | 0
125 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of 'YAAS' 2021 at Alampur water supply scheme, Gopiballavpur-I Block under JMD PHE Dte. (Work Order No.- 656/MMSD-1, Dt-26/05/2021) |  |  | VCH/005498/2021-2022 | BP-2021-22-109 | 09/03/2022 |  | SUBHASIS ROY | 0.55 | 0 | 0 | 0
126 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of 'YAAS' 2021 at Jhargram District Hospital water supply scheme under JMD PHE Dte. (Work Order-660/W/MMD, Dt.-26/05/2021) |  |  | VCH/005512/2021-2022 | BP-2021-22-105 | 09/03/2022 |  | DEBJYOTI BASU | 0.62 | 0 | 0 | 0
127 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of 'YAAS' 2021 at Baligeria water supply scheme, Nayagram Block under JMD PHE Dte. (Work Order No.-657/MMSD-I, Dt.-26/05/2021) |  |  | VCH/005513/2021-2022 | BP-2021-22-105 | 09/03/2022 |  | DEBJYOTI BASU | 0.54 | 0 | 0 | 0
128 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of 'YAAS' 2021 at Nayanagora water supply scheme under JMD PHE Dte. (Work Order No.- 652/MMSD-I, Dt.-26/05/2021) |  |  | VCH/005514/2021-2022 | BP-2021-22-105 | 09/03/2022 |  | DEBJYOTI BASU | 1.27 | 0 | 0 | 0
129 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of 'YAAS' 2021 at Tarafeni water supply scheme under JMD PHE Dte. (Work order No.-651/MMSD-I, Dt.-26/05/2021) |  |  | VCH/005515/2021-2022 | BP-2021-22-105 | 09/03/2022 |  | DEBJYOTI BASU | 0.85 | 0 | 0 | 0
130 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Restoration of water supply arrangement by providing auxilary power by hired DG sets including allied works at different PWSS, Hospitals, Municipality & MTU in C/W Cyclone Yash under District Purba Medinipur, Paschim Medinipur. | SM/09023 | Disaster | Emergency hiring charges of Diesel Generating set on the situation of 'YAAS' 2021 at Rohini water supply scheme, Sankrail Block under JMD PHE Dte. (Work order No.-658/MMSD-I, Dt.-26/05/2021) |  |  | VCH/005516/2021-2022 | BP-2021-22-105 | 09/03/2022 |  | DEBJYOTI BASU | 0.45 | 0 | 0 | 0
Total | [13 empty] | 261.53 | 184.01 | 70.36