## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Gholpukuria PWSS (Zone I) (Phase-III) Balance Part under Nandigram - II Dev. Block. | SM/09049 | Retrofitting | Retrofitting to accommodate FHTC (505 Nos) (Mouza- Rankinipur, J.L. No.-135) & Relaying of damaged pipeline within Nodal point 160-161, 196-197, 196-199, 161-172 & 172-174 in Hanubhunia Mouza, J.L. No.-133, under JJM in Gholepukuria (Zone-I) PWSS (Phase-III) balance part, Block- Nandigram-II in the District of Purba Medinipur. (Part-A) | Assistant Engineer |  | ORD/000125/2021-2022 | 1005/TD | 02/11/2021 | 02/12/2021 | PULAK KUMAR SAMANTA | 11.81 | 11.81 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Gholpukuria PWSS (Zone I) (Phase-III) Balance Part under Nandigram - II Dev. Block. | SM/09049 | Retrofitting | Retrofitting to accommodate FHTC (505 Nos) (Mouza- Rankinipur, J.L. No.-135) & Relaying of damaged pipeline in Hanubhunia Mouza, J.L. No.-133, under JJM in Gholepukuria (Zone-I) PWSS (Phase-III) balance part, Block- Nandigram-II in the District of Purba Medinipur. (Part-B) | Assistant Engineer |  | ORD/000126/2021-2022 | 1006/TD | 02/11/2021 | 02/12/2021 | ZENITH CONSTRUCTION | 28.92 | 7.9 | 27.33 | 100
Total | [13 empty] | 40.73 | 19.71 | 48.4