## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Kudi PWSS under Egra I Block (Phase-II) | SM/09053 | Retrofitting | Retrofitting to accomodate FHTC under JJM in KUDI PWSS Block - Egra-I in the District of Purba Medinipur | Assistant Engineer |  | ORD/000139/2021-2022 | 1022/TD | 02/11/2021 | 22/11/2021 | KESHOB ENTERPRISE | 12.26 | 7.47 | 60.93 | 100
Total | [13 empty] | 12.26 | 7.47 | 60.93