## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | SM/10393 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Monoharpur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000436/2021-2022 | 1512/TD | 06/01/2022 | 26/01/2022 | RADIANT | 3.55 | 3.45 | 97.3 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | SM/10393 | Augmentation | Repairing & Renovation of Pump House No. "1" & Pump House No.- "2" at Manoharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000652/2023-2024 | 2617/TD | 11/10/2023 | 10/11/2023 | ANIRBAN BHOWMIK | 6.15 | 1.59 | 25.85 | 50
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | SM/10393 | Augmentation | Laying of distribution pipe line to accommodate FHTC(2729 Nos) with new construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Manoharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000777/2022-2023 | 2861/TD | 17/02/2023 | 16/08/2023 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 484.9 | 333.78 | 68.83 | 85
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | SM/10393 | Augmentation | Laying of proposed Rising main line with inter connection at Monaharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000981/2023-2024 | 395/TD | 30/01/2024 | 24/02/2024 | G. S. CONSTRUCTION | 9.36 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | SM/10393 | Augmentation | Surging of Deep Tube well at different W/S Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-III) | Assistant Engineer | Junior Engineer | ORD/001164/2023-2024 | 739/HSD, | 19/02/2024 | 05/03/2024 | BUNBA CONSTRUCTION | 2.3 | 1.15 | 50 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | SM/10393 | Augmentation | Construction of Boundary Wall, Protection work ,Earth Filling, Laying of left-out & Parallal Distribution line at Monaharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001208/2023-2024 | 966/TD | 12/03/2024 | 21/04/2024 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 112.45 | 42.99 | 38.23 | 10
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | SM/10393 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 412/TD | 25/05/2022 |  | Resource Division | 47.71 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | SM/10393 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 1266/TD | 12/09/2022 |  | Resource Division | 16.78 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur. | SM/10393 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000065/2023-2024 | 1224/W/MMD | 25/04/2023 | 22/10/2023 | TAPAN KUMAR SARKAR | 24.79 | 0 | 0 | 0
Total | [13 empty] | 707.99 | 382.96 | 54.09