## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Quotation money payment to WBSEDCL for Khejuri Zone-II Water Supply Scheme of Tube Well No. - III |  |  | BILL/00536/2023-2024 | BP-2023-24-284 | 17/08/2023 |  | WBSEDCL | 1.41 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Earth Work in filling in Ditches, Low land at Head Work site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000117/2024-2025 | 1909/TD | 07/06/2024 | 14/06/2024 | TECHNO ENTERPRISE. | 2.02 | 1.01 | 49.89 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 1st Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 2nd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000312/2022-2023 | 1225/TD | 07/09/2022 | 17/10/2022 | M/S SYCHROTECH INDUSTRY | 71.86 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A) | Assistant Engineer | Junior Engineer | ORD/000444/2022-2023 | 1654/TD | 02/11/2022 | 01/05/2023 | SIBSANKAR CHOWDHURY | 449.19 | 0 | 0 | 40
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Construction of boundary wall and construction of Switch Room with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000457/2023-2024 | 1502/TD | 17/07/2023 | 26/08/2023 | RAI CONSTRUCTION | 9.19 | 4 | 43.49 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-I) | Assistant Engineer |  | ORD/000532/2023-2024 | 1858/TD | 09/08/2023 | 19/08/2023 | TECHNO ENTERPRISE. | 0.96 | 0.96 | 99.82 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-II) | Assistant Engineer |  | ORD/000533/2023-2024 | 1859/TD | 09/08/2023 | 19/08/2023 | TECHNO ENTERPRISE. | 0.95 | 0.94 | 99.9 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Construction of Pump Houses and Laying Rising Main for water connection between 1st , 2nd and 3rd Tube Well at Khejuri Water Supply Scheme (Zone-II) within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000733/2023-2024 | 2984/TD | 29/11/2023 | 13/01/2024 | M/S SOURAV MAHAPATRA | 22.43 | 5.11 | 22.76 | 70
9 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-III) | Assistant Engineer | Junior Engineer | ORD/000745/2023-2024 | 3147/TD | 07/12/2023 | 17/12/2023 | TECHNO ENTERPRISE. | 0.91 | 0.45 | 49.97 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 828/TD | 15/07/2022 |  | Resource Division | 60.29 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-I) | SM/10664 | Augmentation | Electric Quotation for Chargeable Head, KHEJURI, Water Supply Scheme T/W-III, Zone-II (Ref. ID-204049542) |  |  | BILL/01673/2023-2024 | null | 01/08/2023 |  | WBSEDCL | 1.41 | 0 | 0 | 0
Total | [13 empty] | 620.61 | 12.47 | 2.01