## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Payment to WBSEDCL for Electric Quotation money of Tabakhali Tube Well No. ¿ III |  |  | BILL/00377/2023-2024 | BP-2023-24-205 | 25/07/2023 |  | WBSEDCL | 0.56 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Way Leave permission from South Eastern Railway for Tabakhali PWSS for Application ID-SER-KGP-2023-WL-67 |  |  | BILL/01828/2023-2024 | BP-2023-24-822 | 22/01/2024 |  | FA & CAO, S.E. RAILWAY, GRC. | 6.17 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000162/2021-2022 | 1166/TD | 01/12/2021 | 08/12/2021 | HORIZEN | 7.85 | 7.74 | 98.54 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000235/2022-2023 | 976/TD | 03/08/2022 | 24/08/2022 | SIMPLEX DRILLING COMPANY | 58.06 | 19.26 | 33.18 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Tabakhali Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000341/2022-2023 | 1284/TD | 12/09/2022 | 11/11/2022 | ELECTIVA ENTERPRISE | 4.77 | 3.37 | 70.53 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Laying left out pipe line,Canal crossing & Rising main of ground water based Tabakhali Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000365/2023-2024 | 933/TD | 01/06/2023 | 11/07/2023 | RAJ KUMAR SINGHA | 81.39 | 65.01 | 79.89 | 88
7 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Construction of boundary wall in 3rd tubewell site of Tabakhali W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | Assistant Engineer | Junior Engineer | ORD/000395/2023-2024 | 1084/TD | 08/06/2023 | 08/07/2023 | M/S SOURAV MAHAPATRA | 5.91 | 1.5 | 25.39 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Tabakhali Water Supply Scheme within Sutahata Dev. Block under Haldia sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000416/2022-2023 | 1578/TD | 14/10/2022 | 12/04/2023 | RAJ KUMAR SINGHA | 709.93 | 326.47 | 45.99 | 55
9 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Jack Pushing of Railway Track Between BASULYA - BARADA Railway Station on Tamluk-Haldia Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Tabakhali Piped Water Supply Scheme of 150 mm Dia G.I. Casing Pipe and 125 mm Dia HDPE (PE-100) Carrier Pipe in between OHE MAST NO H50/11 & H50/13, H50/12 & H50/14 within Haldia Sub-Division under Tamluk Division, P.H.E DTE. (Total Length = 80 Mtr) Nodal Point J38 - J40. | Assistant Engineer | Junior Engineer | ORD/000722/2023-2024 | 2944/TD | 23/11/2023 | 13/12/2023 | KRISHNENDU SEKHAR DAS | 72.62 | 59.1 | 81.39 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 410/TD | 25/05/2022 |  | Resource Division | 205.42 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000087/2022-2023 | 1264/TD | 12/09/2022 |  | Resource Division | 34 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme. | SM/10683 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme Block - Sutahata under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002024/2022-2023 | 862/W/MMD | 27/03/2023 | 23/09/2023 | M/S B ENTERPRISE | 13.41 | 0 | 0 | 70
Total | [13 empty] | 1200.09 | 482.46 | 40.2