## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Estimate for against damage of road flank/hard shoulder due to cutting of hard shoulder and road flank on Bhabanipur-Thekuabazar Road from 5.00 km to 7.00 km for laying of water pipe kline by PHE Department. |  |  | BILL/00232/2023-2024 | BP-2023-24-117 | 14/06/2023 | 14/06/2023 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.76 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-57 under Tamluk Division, PHE Dte. |  |  | BILL/01499/2023-2024 | BP-2023-24-661 | 15/12/2023 | 15/12/2023 | FA & CAO, S.E. RAILWAY, GRC. | 0.28 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Way Leave permission from South Eastern Railway for Jalpai PWSS for Application ID-SER-KGP-2023-WL-59 |  |  | BILL/01829/2023-2024 | BP-2023-24-823 | 22/01/2024 | 22/01/2024 | FA & CAO, S.E. RAILWAY, GRC. | 4.98 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Jalpai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000018/2022-2023 | 52/TD | 05/04/2022 | 25/04/2022 | HORIZEN | 5.57 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 5th tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000068/2023-2024 | 137/TD | 10/04/2023 | 20/05/2023 | GRAND CONSTRUCTION | 5.1 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC (350 nos) with allied works for Augmentation of Jalpai Sater Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-B) | Assistant Engineer | Junior Engineer | ORD/000278/2022-2023 | 1114/TD | 29/08/2022 | 23/09/2022 | SUDIPTA ROY | 75.72 | 0 | 0 | 65
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-C) | Assistant Engineer | Junior Engineer | ORD/000279/2022-2023 | 1115/TD | 29/08/2022 | 15/10/2024 | CHANDIMATA CONSTRUCTION | 72.07 | 0 | 0 | 90
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC (350 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-D) | Assistant Engineer | Junior Engineer | ORD/000280/2022-2023 | 1116/TD | 29/08/2022 | 23/09/2022 | SHAKEEL KHAN | 74.47 | 0 | 0 | 80
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(260 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-H) | Assistant Engineer | Junior Engineer | ORD/000281/2022-2023 | 1117/TD | 29/08/2022 | 18/09/2022 | ADHIKARY CONSTRUCTION | 42.21 | 0 | 0 | 60
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(300 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-I) | Assistant Engineer | Junior Engineer | ORD/000283/2022-2023 | 1118/TD | 29/08/2022 | 23/09/2022 | NARAYAN CHANDRA DAS | 76.58 | 0 | 0 | 80
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-J) | Assistant Engineer | Junior Engineer | ORD/000284/2022-2023 | 1119/TD | 29/08/2022 | 23/09/2022 | S.D. CONSTRUCTION | 70.82 | 0 | 0 | 70
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-K) | Assistant Engineer | Junior Engineer | ORD/000285/2022-2023 | 1120/TD | 29/08/2022 | 24/05/2025 | FARID UDDIN AHMED | 65.7 | 0 | 0 | 91
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(200 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-L) | Assistant Engineer | Junior Engineer | ORD/000286/2022-2023 | 1121/TD | 29/08/2022 | 23/09/2022 | KRISHNENDU SEKHAR DAS | 78.19 | 0 | 0 | 85
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC (100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-M) | Assistant Engineer | Junior Engineer | ORD/000287/2022-2023 | 1122/TD | 29/08/2022 | 18/09/2022 | SK SANAMAJ | 56.8 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-N) | Assistant Engineer | Junior Engineer | ORD/000288/2022-2023 | 1123/TD | 29/08/2022 | 16/12/2024 | BHOLANATH DEY | 57.72 | 0 | 0 | 96
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-O) | Assistant Engineer | Junior Engineer | ORD/000289/2022-2023 | 1124/TD | 29/08/2022 | 18/09/2022 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 56.12 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-Q) | Assistant Engineer | Junior Engineer | ORD/000290/2022-2023 | 1125/TD | 29/08/2022 | 18/09/2022 | S. N. A. CONSTRUCTION | 46.55 | 0 | 0 | 99
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(50 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-R) | Assistant Engineer | Junior Engineer | ORD/000291/2022-2023 | 1126/TD | 29/08/2022 | 13/09/2022 | SAYAN MAITY | 9.94 | 0 | 0 | 80
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(50 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-S) | Assistant Engineer | Junior Engineer | ORD/000292/2022-2023 | 1127/TD | 29/08/2022 | 13/09/2022 | OM UDYOG | 9.85 | 0 | 0 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-P) | Assistant Engineer | Junior Engineer | ORD/000293/2022-2023 | 1128/TD | 29/08/2022 | 18/09/2022 | AQUATECH ENGINEERS | 45.31 | 0 | 0 | 85
21 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(300 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-E) | Assistant Engineer | Junior Engineer | ORD/000294/2022-2023 | 1129/TD | 29/08/2022 | 23/09/2022 | S.K. MONDAL | 72.41 | 0 | 0 | 75
22 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(330 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-F) | Assistant Engineer | Junior Engineer | ORD/000295/2022-2023 | 1130/TD | 29/08/2022 | 23/09/2022 | RELIABLE CONSTRUCTIONS | 72.71 | 0 | 0 | 75
23 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-G) | Assistant Engineer | Junior Engineer | ORD/000296/2022-2023 | 1131/TD | 29/08/2022 | 23/09/2022 | DILIP KUMAR GHOSH | 73.9 | 0 | 0 | 99
24 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Laying of Distribution pipe line to accommodate FHTC(3600 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Jalpai Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-A) | Assistant Engineer | Junior Engineer | ORD/000385/2022-2023 | 1386/TD | 23/09/2022 | 22/03/2023 | M/S. CARE | 454 | 0 | 0 | 30
25 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 2nd Tubewell Site of Natshal Lakshya Zone - I W/S Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 5th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 4th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000543/2023-2024 | 1905/TD | 10/08/2023 | 19/09/2023 | AQUATECH ENGINEER | 58.34 | 0 | 0 | 45
26 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000664/2022-2023 | 2349/TD | 10/01/2023 | 19/02/2023 | RAI CONSTRUCTION | 5.06 | 0 | 0 | 10
27 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000665/2022-2023 | 2350/TD | 10/01/2023 | 19/02/2023 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 5.06 | 0 | 0 | 0
28 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 1374/TD | 23/09/2022 | 23/09/2022 | Resource Division | 48.52 | 0 | 0 | 0
29 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2022-2023 | 1672/TD | 03/11/2022 | 03/11/2022 | Resource Division | 373.53 | 0 | 0 | 0
30 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000205/2023-2024 | 1104/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
31 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & above) having contract carriage permit along with driver for the office of the Driller in charge, CMSD-II(D), CDD, PHE Dte. |  |  | ORD/000003/2023-2024 | 107/CMSD-II | 27/04/2023 | 28/10/2023 | ASHUTOSH PAL | 0.87 | 0 | 0 | 33
32 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR JAIPAI W/S SCHEME (TW-I), NANDAKUMAR BLOCK UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000414/2022-2023 | 1637/CDD | 20/12/2022 | 19/01/2023 | DEY ENTERPRISE | 19.2 | 0 | 0 | 0
33 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Quotation Bill For New Service Connection at TW-IV of Jalpai PWSS under MMD PHE Dte.,Block-Nandakumar C.C.C.-Na Contract Demand-12000Wndakumar Application no.-2004653153 Application Type-New Connection Quotation Date-28/03/2024 Quotation Due Date-28/03/2025 |  |  | BILL/00252/2024-2025 | BP-2024-25-26 | 15/04/2024 | 15/04/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
34 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Jalpai W/S scheme TW-III Application No.-2004554813 Ref.-204184634 |  |  | BILL/03346/2023-2024 | BP-2023-24-576 | 18/01/2024 | 18/01/2024 | WBSEDCL | 3.46 | 0 | 0 | 0
35 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at JALPAI Water supply scheme,T/W - V, NANDAKUMAR block, District ¿ Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000390/2024-2025 | 2006/W/MMD | 30/08/2024 | 26/02/2025 | M/S EMMESS | 14.12 | 0 | 0 | 0
36 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipment's for augmentation of ground water based Jaipai w/s scheme under JJM Program under Medinipur Mechanical Division P.H.E Dte. In the dist of PurbaMedinipur. |  | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000427/2023-2024 | 580/HESD | 04/08/2023 | 11/08/2023 | BHABANI PRASAD MANNA | 0.39 | 0 | 0 | 0
37 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water based Jalpai Water Supply Scheme. | SM/11920 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water based Jalpai Water Supply Scheme, Block ¿ Nanda Kumar, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001512/2022-2023 | 356/W/MMD | 09/03/2023 | 05/09/2023 | BHABANI PRASAD MANNA | 40.78 | 0 | 0 | 60
Total | [13 empty] | 2102.5 | 0 | 0