## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1914 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SOYA DIGHI PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000205/2023-2024 | 412/TD | 02/05/2023 | 29/10/2023 | JAYANTA KUMAR MONDAL | 418.27 | 36.58 | 8.74 | 25
2 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Soya Dighi PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. |  |  | ORD/000229/2024-2025 | 2424/TD | 29/07/2024 | 08/08/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | New | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 110/TD | 05/01/2024 |  | Resource Division | 11.79 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | New | Material Requisition To Resource Division |  |  | RTOR000257/2022-2023 | 2680/TD | 06/02/2023 |  | Resource Division | 20.04 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SOYA DIGHI and ADJOINING MOUJAS, Block - Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002035/2022-2023 | 943/W/MMD | 28/03/2023 | 24/09/2023 | ORIENTAL ENGINEERING CO. | 22.79 | 0 | 0 | 0
Total | [13 empty] | 473.85 | 36.58 | 7.72