## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai - I | Tamluk Division | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 22/04/2024 | MACKINTOSH BURN LIMITED | 10310.59 | 0 | 0 | 12
2 | PURBA MEDINIPUR | Contai - I | Tamluk Division | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Material Requisition To Resource Division |  |  | RTOR000171/2022-2023 | 2395/TD | 16/01/2023 |  | Resource Division | 25.23 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Contai - I | Midnapore Mechanical | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001711/2022-2023 | 594/W/MMD | 20/03/2023 | 16/09/2023 | INDIA ENTERPRISE | 21.62 | 0 | 0 | 0
Total | [13 empty] | 10357.45 | 0 | 0