## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | SM/16458 | Augmentation | Laying of Distribution pipe line,Rising main pipe line, Pump House, Boundary Wall, with allied works of MANDARMANI & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Phase-III) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 842/TD | 31/05/2023 | 10/07/2023 | DILIP KUMAR GHOSH | 94.7 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | SM/16458 | Augmentation | Pipe crossing for laying Distribution pipe line to provide FHTC (9 nos.) of Mondarmoni W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (NP- 8 - 6, NP- 48 - 50, NP-50 - 52) | Assistant Engineer |  | ORD/000373/2023-2024 | 1010/TD | 05/06/2023 | 25/06/2023 | UNIQUE AGENCY | 7.52 | 7.52 | 100 | 100
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) | SM/16458 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001999/2022-2023 | 901/W/MMD | 27/03/2023 | 23/09/2023 | S.S.GHORAI | 12.63 | 0 | 0 | 0
Total | [13 empty] | 114.85 | 7.52 | 6.55