## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. | SM/16463 | Augmentation | Way Leave permission from South Eastern Railway for Lakshya PWSS for Application ID-SER-KGP-2023-WL-66 |  |  | BILL/01827/2023-2024 | BP-2023-24-821 | 22/01/2024 |  | FA & CAO, S.E. RAILWAY, GRC. | 6.52 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. | SM/16463 | Augmentation | Laying of Distribution pipe line for FHTC (920 nos), Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Lakshya & its adjoining mouzas Water Supply Scheme within Mahisadal Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000124/2023-2024 | 254/TD | 19/04/2023 | 19/05/2023 | HARIPADA PATTANAYAK | 64.14 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. | SM/16463 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002001/2022-2023 | 903/W/MMD | 27/03/2023 | 23/09/2023 | RITESH ENTERPRISE | 13.59 | 0 | 0 | 0
Total | [13 empty] | 84.25 | 0 | 0