## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | New | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at KUMARGRAM W/S Scheme TW NO- II under NMD-II, P.H.E. Dte.Alipurduar. |  |  | ORD/000019/2020-2021 | 1049/NMD-II | 04/09/2020 | 04/10/2020 | MAA ENTERPRISES | 3.12 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | New | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at KUMARGRAM W/S Scheme TW NO-I under NMD-II, P.H.E. Dte.Alipurduar. |  |  | ORD/000023/2020-2021 | 1038/NMD-II | 04/09/2020 | 04/10/2020 | HARA PROSAD DAS | 3.12 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | New | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at KUMARGRAM W/S Scheme TW NO- III under NMD-II, P.H.E. Dte.Alipurduar. |  |  | ORD/000041/2020-2021 | 1113/NMD-II | 08/10/2020 | 07/11/2020 | MALAY KUMAR SAHA | 3.12 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | New | Operation and Guarding of Pumping machinery at Pump House No. II under KUMARGRAM W/S Scheme. In the dist. Of ALIPURDUAR. |  |  | ORD/000500/2021-2022 | 633/NMD-II | 06/07/2021 | 06/07/2022 | DIAMOND ELECTRICAL WORKS | 4.88 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | New | Operation and Guarding of Pumping machinery at Pump House No. III under KUMARGRAM W/S Scheme. In the dist. Of ALIPURDUAR. |  |  | ORD/000501/2021-2022 | 634/NMD-II | 06/07/2021 | 06/07/2022 | SUNLIT | 4.88 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kumargram block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000520/2021-2022 | 1076/NMD-II | 10/09/2021 | 30/09/2021 | M/S P.P ELECTRICALS | 3.58 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at different PWSS under Kumargram Block in the District of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000531/2020-2021 | 1316/NMD-II | 29/12/2020 | 18/01/2021 | SUMON ELECTRICAL | 1.79 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Barovisa, Radharani etc under Kumargram & Kalchini block in the dist. of Alipurduar¿ |  |  | ORD/000702/2021-2022 | 1313/NMD-II | 03/12/2021 | 18/12/2021 | DIPA CHHETRI | 1.29 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | New | Withdrawing 15 HP capacity submersible pumpset and lowering same set after necessary repairing and overhauling at T.W.No-I, under Kumargram W/S scheme,in the dist. Alipurduar , AMSD ,PHE Dte. |  |  | ORD/000784/2020-2021 | 860/AMSD | 29/01/2021 | 08/02/2021 | SARKAR ELECTRIC | 0.31 | 0 | 0 | 0
Total | [13 empty] | 26.09 | 0 | 0