## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | UTTAR MAJHERDABARI WATER SUPPLY SCHEME | SM/00152 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under UTTAR MAJHERDABARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000313/2021-2022 | 622/NMD-II | 06/07/2021 | 06/07/2022 | UTTAM PAUL | 4.88 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | UTTAR MAJHERDABARI WATER SUPPLY SCHEME | SM/00152 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under UTTAR MAJHERDABARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000391/2021-2022 | 558/NMD-II | 06/07/2021 | 06/07/2022 | UTTAM PAUL | 4.88 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | UTTAR MAJHERDABARI WATER SUPPLY SCHEME | SM/00152 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | UTTAR MAJHERDABARI WATER SUPPLY SCHEME | SM/00152 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Shamultala,Loknathpur etc under Alipurduar-I& II Block in the dist. of Alipurduar¿ |  |  | ORD/000703/2021-2022 | 1314/NMD-II | 03/12/2021 | 18/12/2021 | M/S KUNDU CONSTRUCTION | 2.29 | 0 | 0 | 0
Total | [13 empty] | 15.63 | 0 | 0