## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Parokata water supply scheme | SM/01378 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under MADHYA PAROKATA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000359/2021-2022 | 726/NMD-II | 08/07/2021 | 08/07/2022 | M/S CHANDRANATH MUKHERJEE | 2.97 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Parokata water supply scheme | SM/01378 | New | Internal wiring & Earthing arrangement & allied works at P/H No.I of Madhya Parokata W/S Scheme at under AMSD , PHE Dte. In the dist. of Alipurduar |  |  | ORD/000806/2020-2021 | 400/AMSD | 07/08/2020 | 17/08/2020 | TALUKDAR ENTERPRISE | 0.18 | 0 | 0 | 0
Total | [13 empty] | 3.15 | 0 | 0