## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - II | Jalpaiguri Division | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | SWSM -- Ground water based water supply scheme for Salsalabari and adjoining mouza(SM/04011) |  |  | VCH/001027/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 1.44 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - II | Northern Mechanical | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - II | Northern Mechanical | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Consolidated Supply Bills |  |  | VCH/001041/2018-2019 | 1216/W/18-19 | 16/03/2019 |  | ALPHA ENTERPRISE | 1.57 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Construction of approach road & car parking area with paver block & chequered tiles at Jainty WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - I Block | ORD/000331/2021-2022 | 2107/ALD | 05/01/2022 | 04/02/2022 | DAS ENTERPRISE | 5.02 | 0 | 0 | 77
5 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under SALSALABARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000370/2021-2022 | 733/NMD-II | 08/07/2021 | 08/07/2022 | CHOWDHURY AND BASU ENTERPRISE | 2.97 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Supply, delivery of Electro Mechanical components at SALSALABARI Water Supply Scheme IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000586/2020-2021 | 1508/NMD-II | 11/02/2021 | 13/03/2021 | BONANZA ENTERPRISE | 9.06 | 9.06 | 100 | 0
8 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Supply, delivery of Electro Mechanical components at Salsalabari Water Supply Scheme,T/W No-II IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000587/2020-2021 | 1509/NMD-II | 11/02/2021 | 13/03/2021 | S.K ELECTRICALS | 6.43 | 6.07 | 94.43 | 0
9 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at differernt PWSS under Alipurduar-II Block in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000598/2021-2022 | 1043/NMD-II | 03/09/2021 | 23/09/2021 | WEST BENGAL ENGINEERING CO. | 3.5 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under SALSALABARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000657/2021-2022 | 774/NMD-II | 08/07/2021 | 08/07/2022 | M/S RATAN KUMAR DASGUPTA & CO. | 2.97 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Salsalabari Water Supply Scheme TW No.-III under NMD-II,PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000755/2021-2022 | 68/NMD-II | 24/01/2022 | 23/02/2022 | SUBODH KUMAR BANIK | 7.8 | 6.18 | 79.26 | 100
12 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | Quotation for new service connection at Salsalabat TW NO-III |  |  | VCH/001060/2021-2022 | null | 17/11/2021 |  | WBSEDCL | 0.76 | 0 | 0 | 0
13 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | New | New connection of Salsala bari P/H no. III Aplication no. 4002754391 |  |  | VCH/001462/2021-2022 | BP-2021-22-18 | 22/11/2021 |  | WBSEDCL | 0.76 | 0 | 0 | 0
Total | [13 empty] | 101.37 | 21.32 | 21.03