## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Jalpaiguri Division | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | DHUMCHIPARA T.G |  |  | VCH/001044/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 0.15 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Consolidated Supply Bills |  |  | VCH/000971/2018-2019 | 1142/W/18-19 | 01/03/2019 |  | S.P. ENTERPRISE | 1.39 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Alipurduar Division | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Construction of approach road & car parking area with paver block & chequered tiles at Jainty WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - I Block | ORD/000331/2021-2022 | 2107/ALD | 05/01/2022 | 04/02/2022 | DAS ENTERPRISE | 5.02 | 0 | 0 | 77
5 | ALIPURDUAR | Madarihat | Alipurduar Division | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under DHUMCHIPARA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000333/2021-2022 | 700/NMD-II | 08/07/2021 | 08/07/2022 | B.B CONCERNED | 2.97 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under DHUMCHIPARA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000344/2021-2022 | 711/NMD-II | 08/07/2021 | 08/07/2022 | M/S PALI DEB ENGINEERING | 2.97 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Operation and Guarding of Pumping machinery at Pump House No. III under DHUMCHIPARA TG W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000492/2021-2022 | 754/NMD-II | 08/07/2021 | 08/07/2022 | S.P ENTERPRISE (SLG) | 2.97 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Supply & delivery of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at Dekhlapara T.G P/H No.-I , Birpara p/H No.I, Paschim Khairbari P/H No.II ,Gargenda P/h No.II, Dhumchipara P/HNo.I in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000522/2021-2022 | 1070/NMD-II | 10/09/2021 | 30/09/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.76 | 0 | 0 | 0
11 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I&II under Satkura and Salmara P/H No.I PWSS in the district of Coochbehar under NMD-II ,P.H.E Dte. |  |  | ORD/000569/2021-2022 | 1014/NMD-II | 27/08/2021 | 16/09/2021 | SUNLIT | 2.6 | 0 | 0 | 0
12 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Supply, delivery of Electro Mechanical components at DHUMCHIPARA TEA GARDEN Water Supply Scheme IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000574/2020-2021 | 1455/NMD-II | 02/02/2021 | 04/03/2021 | M/S SUDIP DUTTA & CO. | 7.29 | 7.29 | 100 | 0
13 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | "Supply, delivery and installation of Actuator operated wafer type butterfly valve under Dhumchipara tea garden water supply scheme, TW-II in the district of Alipurduar" |  |  | ORD/000597/2020-2021 | 849/AMSD | 27/01/2021 | 06/02/2021 | B.B CONCERNED | 0.89 | 0 | 0 | 0
14 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Supply and delivery of PVC coated steel rope & Metal clamp at Dhumchipara T.G W/S scheme for T.W No. -III in the dist. of Alipurduar. |  |  | ORD/000604/2021-2022 | 310/AMSD | 16/08/2021 | 26/08/2021 | B.B CONCERNED | 0.39 | 0.39 | 100 | 0
15 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Operation & guarding of the pumping machinery at Pump House No. III under DHUMCHIPARA TG W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000693/2020-2021 | 650/AMSD | 12/11/2020 | 08/03/2021 | S.P ENTERPRISE (SLG) | 0.93 | 0 | 0 | 0
16 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. III under DHUMCHIPARA TG W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000756/2020-2021 | 983/AMSD | 23/03/2021 | 21/07/2021 | S.P ENTERPRISE (SLG) | 0.96 | 0 | 0 | 0
17 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Supply & delivery of standby submersible pump for Dhumchipara Tea garden W/S scheme,P/H no. I in the district of Alipurduar under Northern Mechanical Division-II,PHE Dte |  |  | ORD/000763/2020-2021 | 767/AMSD | 28/12/2020 | 07/01/2021 | SUMON ELECTRICAL | 0.67 | 0 | 0 | 0
18 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | Supply, delivery,of Electro mechanical components at Dhumchipara T.G Water Supply Scheme and other adjacent mouzas ,in the dist of ALIPURDUAR under NMD-II PHE Dte Alipurduar. |  |  | ORD/000876/2021-2022 | 354/NMD-II | 15/03/2022 | 14/04/2022 | ALPHA ENTERPRISE | 8.77 | 6.63 | 75.56 | 0
19 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | New | WBSEDCL Quotation for Dhumchipara T.G, W/S scheme, T/W No. III. Application No. 4002465025 |  |  | VCH/000929/2019-2020 | 117/19-20 | 03/02/2020 |  | WBSEDCL | 2.01 | 0 | 0 | 0
Total | [13 empty] | 606.53 | 14.3 | 2.36