## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Barasat Arsenic Division | Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme | SM/06374 | New | Procurement of 1 no. of Mobile Laboratory Van (MLV) complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with OMAS instruments, devices, consumables, reagents, smart phone with preloaded water quality app synchronized with PHED water quality dashboard and safety gear for resource personnel for water quality testing in remote areas including external designing and painting for IEC propaganda complete with IEC audio visual aids as directed by EIC for Northern Zone of West Bengal under Public Health Engineering Department, Govt. of West Bengal. |  |  | ORD/000235/2018-2019 | 454 / B.Ar.D | 21/02/2019 | 16/02/2020 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 75.86 | 0 | 0 | 100
Total | [13 empty] | 75.86 | 0 | 0