## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | SUPPLY OF HSD FOR THE MONTH OF DECEMBER 2021 UNDER ALIPURDUAR DIVISION PHED |  |  | VCH/001108/2021-2022 | 378/21-22 | 28/12/2021 |  | SHIVAM SERVICE STATION | 0.17 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Supply, delivery & installation of Electro Mechanical Components at RADHARANI W/S Scheme, P/H No. IV(Near Chuapara), under NMD-II, PHE, Dte. in the dist of Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000058/2023-2024 | 113/AMSD | 16/06/2023 | 06/07/2023 | MUSTAFI CONCERN | 6.67 | 5.99 | 89.92 | 90
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Outdoor illumination and other allied works at site office cum godown under Radharani water supply scheme under NMD-II ,PHE.Dte,Alipurduar. |  |  | ORD/000336/2022-2023 | 225/AMSD | 21/07/2022 | 05/08/2022 | CHOWDHURY AND BASU ENTERPRISE | 4.4 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Withdrawing of 10 HP Submersible pump machinery along with supply and installation of electro mechanical accessories under RADHARANI TG WATER SUPPLY SCHEME,P/H No-I under Northern Mechanical Division-II Phe. Dte. In the dist. Of Alipurduar. |  |  | ORD/000653/2021-2022 | 1099/NMD-II | 20/09/2021 | 20/10/2021 | B.B CONCERNED | 2.06 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Operation and Guarding of Pumping machinery at Pump House No. I, Under RADHARANI T.G W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000674/2021-2022 | 1218/NMD-II | 28/10/2021 | 28/07/2022 | B.B CONCERNED | 2.22 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Operation and Guarding of Pumping machinery at Pump House No. II, Under RADHARANI T.G W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000678/2021-2022 | 1214/NMD-II | 28/10/2021 | 28/07/2022 | SUMON ELECTRICAL | 2.22 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Supply and delivery of Standby Submersible pumping Machinery for Emergency Breakdown at Pump House I Under Radharani TG Water Supply Scheme under NMD-II,PHE Dte,Dist-Alipurduar. |  |  | ORD/000700/2021-2022 | 463/AMSD | 22/11/2021 | 02/12/2021 | SUMON ELECTRICAL | 0.49 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Barovisa, Radharani etc under Kumargram & Kalchini block in the dist. of Alipurduar¿ |  |  | ORD/000702/2021-2022 | 1313/NMD-II | 03/12/2021 | 18/12/2021 | DIPA CHHETRI | 1.29 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Supply, delivery & installation of 15 KVA, Servo Motor operated Copper wound line voltage stabilizer of Radharani T.G Water Supply Scheme TW No.-III under NMD-II,PHE. Dte, Alipurduar. |  |  | ORD/000723/2021-2022 | 1378/NMD-II | 22/12/2021 | 21/01/2022 | MADHAB SAHA | 2.16 | 0.11 | 4.87 | 0
10 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of RADHARANI T.G Water Supply Scheme TW No.-III under NMD-II,PHE Dte. Alipurduar. |  |  | ORD/000757/2021-2022 | 70/NMD-II | 24/01/2022 | 23/02/2022 | CHOWDHURY AND BASU ENTERPRISE | 7.35 | 7.35 | 100 | 0
11 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Supply, delivery of Electro mechanical components at Radharani T.G Water Supply Scheme and other adjacent mouzas in the dist of ALIPURDUAR under NMD-II PHE Dte Alipurduar. |  |  | ORD/000878/2021-2022 | 369/NMD-II | 16/03/2022 | 15/04/2022 | CHOWDHURY AND BASU ENTERPRISE | 13.09 | 13.09 | 100 | 100
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Quotation for new Connection at Radharani T.G, P/H No. I. Application No. 4002487944 |  |  | VCH/001454/2019-2020 | 142/19-20 | 19/02/2020 |  | WBSEDCL | 0.92 | 0 | 0 | 0
13 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Quotation for new Connection at Radharani T.G, P/H No. II. Application No.4002487938 |  |  | VCH/001455/2019-2020 | 142/19-20 | 19/02/2020 |  | WBSEDCL | 0.92 | 0 | 0 | 0
14 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Quotation for new service connection at Radharani TG TW No-III |  |  | VCH/002430/2021-2022 | null | 15/02/2022 |  | WBSEDCL | 0.92 | 0 | 0 | 0
15 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | New | Quotation for new service connection at Radharani W?SS TW -III |  |  | VCH/002431/2021-2022 | null | 15/02/2022 |  | WBSEDCL | 0.92 | 0 | 0 | 0
Total | [13 empty] | 45.81 | 26.54 | 57.94