## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME | SM/10667 | Augmentation | Providing balance FHTC for Bakla PWSSunder Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000206/2023-2024 | 1560/ALD | 23/08/2023 | 22/09/2023 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 2.47 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME | SM/10667 | Augmentation | Laying distribution system with new UPVC pipeline and others allied works for providing functional household Tap Connection(FHTC) in connection with the Augmentation of Bakla PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000321/2022-2023 | 2230/ALD | 21/11/2022 | 20/01/2023 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 42.04 | 40.79 | 97.04 | 23
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME | SM/10667 | Augmentation | Laying of new UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Bakla PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000351/2023-2024 | 2603/ALD | 04/12/2023 | 03/03/2024 | SHYAMAL ROY | 32.04 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME | SM/10667 | Augmentation | Land Development, Paver Block installation and Laying and distribution of UPVC pipeline at 2nd Pumphouse site and Adjacent Area of Bakla PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000487/2022-2023 | 3319/ALD | 13/03/2023 | 11/06/2023 | SHYAMAL ROY | 11.1 | 10.92 | 98.33 | 100
5 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF BAKLA WATER SUPPLY SCHEME | SM/10667 | Augmentation | Quotation for new service connection at Bakla P/H No- III, Application NO- 4003022080 |  |  | BILL/00008/2022-2023 | null | 28/11/2022 |  | WBSEDCL | 1.37 | 0 | 0 | 0
Total | [13 empty] | 89.02 | 51.71 | 58.09