## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME | SM/10671 | Augmentation | Dismantling Concrete road and re -casting the same for providing FHTC at different area of BIRPARA (APD) PWSS AND Alipurduar - I Block under Alipurduar Division , PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000078/2022-2023 | 441/ALD | 13/05/2022 | 12/06/2022 | R.K.CONSTRUCTION | 4.96 | 0 | 0 | 70.5
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME | SM/10671 | Augmentation | Extension and replacement of damaged pipeline of Birpara PWSS, Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000295/2022-2023 | 1686/ALD | 20/09/2022 | 19/11/2022 | KAMALESH ROY | 5.01 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME | SM/10671 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BIRPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000316/2021-2022 | 2192/ALD | 11/01/2022 | 11/04/2022 | DAS CONSTRUCTION | 22.03 | 4.04 | 18.34 | 65
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME | SM/10671 | Augmentation | Laying of UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Birpara(APD) PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000348/2023-2024 | 2600/ALD | 04/12/2023 | 03/03/2024 | DAS CONSTRUCTION | 38.1 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF BIRPARA (APD) WATER SUPPLY SCHEME | SM/10671 | Augmentation | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Birpara PWSS (APD) Under Alipurduar Division, PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000443/2021-2022 | 2751/ALD | 24/02/2022 | 25/04/2022 | R.K.CONSTRUCTION | 31.74 | 14.75 | 46.46 | 59.75
Total | [13 empty] | 101.83 | 18.79 | 18.45