## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | SM/10676 | Augmentation | Laying of DI pipe of Different Dia and other works For TAPSHIKHATA PWSS at Alipurduar -I Block under Alipurduar Division , PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000070/2022-2023 | 435/ALD | 13/05/2022 | 12/06/2022 | KAMALESH ROY | 4.76 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | SM/10676 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000349/2021-2022 | 2142/ALD | 06/01/2022 | 05/02/2022 | DEBAJYOTI SUTRADHAR | 5.02 | 5.02 | 99.99 | 52.25
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TAPASHIKHATA PIPED WATER SUPPLY SCHEME | SM/10676 | Augmentation | Laying of distribution line with HDPE,UPVC and CI/DI pipes, laying of paver block at pump house no-1 and 2 and providing FHTC for Aug. Of Tapshikhata PWSS under Alipurduar Division. | Alipurduar RWS,Alipurduar Sadar Sub Division | Birpara Sub Division,JUNIOR ENGINEER | ORD/000469/2023-2024 | 675/ALD | 06/03/2024 | 02/09/2024 | TAPASH DAS | 43.25 | 13.49 | 31.19 | 10
Total | [13 empty] | 53.02 | 18.51 | 34.9