## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Tubewell boring by ODEX-165 method of drilling, construction of Pump House, Boundary wall at proposed 4th TW site of Kaijali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000004/2023-2024 | 07/ALD | 04/04/2023 | 02/08/2023 | PRITAM DAS | 17.41 | 10.87 | 62.45 | 100
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Land development works, Construction of surface drain, pathway, and other allied works at Kaijali Busty 4th tube well site with the Augmentation of Kaijali Busty PWSS Under Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE.(SM/11958) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000220/2024-2025 | 2273/ALD | 05/08/2024 | 04/10/2024 | RAMEN DEY & CO | 4.28 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Land development works, Construction of surface drain, pathway, and other allied works at Kaijali Busty 3rd tube well site with the Augmentation of Kaijili Busty PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE.(SM/11958) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000221/2024-2025 | 2274/ALD | 05/08/2024 | 04/10/2024 | KAMALESH ROY | 3.84 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Tube well Boring by ODEX-165 method of drilling at 3rd TWsite including laying Distribution system with new HDPE Pipeline (Part-A), Providing FHTC and other allied works for augmentation of KAIJALI BUSTY PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000331/2022-2023 | 2240/ALD | 21/11/2022 | 15/03/2024 | KAMALESH ROY | 70.16 | 44.79 | 63.84 | 68
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Soil investigation works for proposed overhead reservoir of KAIJALI BUSTI PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000339/2022-2023 | 2248/ALD | 21/11/2022 | 21/12/2022 | K S GROUP | 0.65 | 0.65 | 100 | 11
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Construction of 200 cum OHR as per Departmental Design and drawing at KAIJALI BUSTY PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000353/2022-2023 | 2497/ALD | 13/12/2022 | 05/06/2024 | MAHENDRA CHHETRI | 68.63 | 33.16 | 48.32 | 70
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 1588/ALD | 14/09/2022 |  | Resource Division | 30.75 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | QUATATION |  |  | BILL/02208/2023-2024 | BP-2023-24-484 | 12/12/2023 |  | WBSEDCL | 5.11 | 0 | 0 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | QUOTATION |  |  | BILL/02209/2023-2024 | BP-2023-24-485 | 12/12/2023 |  | WBSEDCL | 11.22 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Kaijali Basty Water Supply Scheme TW No.- I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000893/2023-2024 | 2480/NMD-II | 11/08/2023 | 10/09/2023 | DIAMOND ELECTRICAL WORKS | 25.08 | 5.87 | 23.41 | 90
Total | [13 empty] | 237.14 | 95.35 | 40.21