## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Restoration of DI pipe crossing near CHOR TORSHA and other repair works in Banshidharpur area under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000035/2023-2024 | 366/ALD | 18/05/2023 | 17/06/2023 | NARENDRA BHADANI. | 1.42 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Continuation work order for the work of "Sinking of Rig bore T/W (4nos.) by Reverse Rotary method of drilling, cons. of 100 cum. OHR (2nos), cons. of P/H and B/W, Rising main, distribution line and providing FHTC at H/W and 2nd site inclu. Soil testing for KADAMBINI TG PWSS (ZONE-I and ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/5/2024-EE(ALI_D) SEC-DPHE (Computer No-973264)) | Birpara A.E | RWS Falakata Block | ORD/000199/2024-2025 | 1913/ALD | 26/06/2024 | 25/08/2024 | DILIP MAHATO | 14.57 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Laying leftout pipeline (not including at Lop of pipeline) at kadambini TG PWSS (Zone-I & II) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000344/2024-2025 | 3233/ALD | 10/09/2024 | 09/11/2024 | DILIP MAHATO (OPC) PRIVATE LIMITED | 25.1 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Sinking of Rig bore T/W (4nos.) by Reverse Rotary method of drilling, cons. of 100 cum. OHR (2nos), cons. of P/H and B/W, Rising main, distribution line and providing FHTC at H/W and 2nd site inclu. Soil testing for KADAMBINI TG PWSS (ZONE-I and ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte | Birpara A.E | RWS Falakata Block | ORD/000430/2022-2023 | 2857/ALD | 17/01/2023 | 16/07/2023 | DILIP MAHATO | 498.42 | 352.5 | 70.72 | 72
5 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | "Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Kadambini TG Water Supply Scheme (SM/13239) of Falakata Block under Alipurduar Division P.H.E. Dte. " | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000526/2023-2024 | 845/ALD | 14/03/2024 | 13/04/2024 | MANSAROVAR CASTING | 13.2 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1274/ALD | 11/08/2023 |  | Resource Division | 34.39 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-II,Z-II |  |  | BILL/00058/2023-2024 | BP-2023-24-52 | 15/05/2023 |  | WBSEDCL | 1.37 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-I,Z-II |  |  | BILL/00059/2023-2024 | BP-2023-24-54 | 15/05/2023 |  | WBSEDCL | 1.37 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-I,Z-I |  |  | BILL/00060/2023-2024 | BP-2023-24-53 | 15/05/2023 |  | WBSEDCL | 1.37 | 0 | 0 | 0
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-II,Z-I |  |  | BILL/00061/2023-2024 | BP-2023-24-55 | 15/05/2023 |  | WBSEDCL | 1.37 | 0 | 0 | 0
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Additional Quotation for New Service connection charges for Kadambini T.G PWSS, Zone-I,P/H No-I |  |  | BILL/02622/2023-2024 | BP-2023-24-588 | 02/02/2024 |  | WBSEDCL | 11.92 | 0 | 0 | null
12 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | ADDITIONAL QUOTATION FOR NEW SERVICE CONNECTION CHARGES FOR KADAMBINI T.G PWSS, ZONE-I,P/HNO-II |  |  | BILL/02750/2023-2024 | BP-2023-24-621 | 20/02/2024 |  | WBSEDCL | 5.15 | 0 | 0 | null
13 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kadambini water supply scheme, TW no I and II of Zone-II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000854/2023-2024 | 2437/NMD-II | 11/08/2023 | 10/09/2023 | A.G ENTERPRISE | 18.46 | 8.58 | 46.49 | 90
14 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kadambini water supply scheme, TW no I and II of Zone-I under Northern Mechanical Division-II, PHE Dte.Alipurduar. |  |  | ORD/001090/2023-2024 | 2792/NMD-II | 06/10/2023 | 05/11/2023 | ASHUTOSH DAS & CO. | 18.45 | 0 | 0 | 0
Total | [13 empty] | 646.56 | 361.08 | 55.85