## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME | SM/13246 | New | Boring of TW, Cons. Of Pump House, boundary wall, OHR (400 cum) inclu. Soil investigation works, Laying of rising main, distribution system and providing FHTC for BARIGURI PWSS under Alipurduar Division PHE DTE. (2nd call) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000029/2023-2024 | 333/ALD | 16/05/2023 | 06/11/2024 | MESSRS A.B.G CONSTRUCTION | 592.24 | 132.3 | 22.34 | 4
2 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME | SM/13246 | New | Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Bairiguri Water Supply(SM/13246) of Alipurduar-I Block Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000216/2024-2025 | 2068/ALD | 12/07/2024 | 11/08/2024 | BARMAN ENTERPRISE | 11.35 | 5.05 | 44.52 | 100
3 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME | SM/13246 | New | Providing FHTC from existing distribution system as per specification for Bariguri PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000259/2023-2024 | 1877/ALD | 07/09/2023 | 07/10/2023 | DAS CONSTRUCTION | 8.1 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME | SM/13246 | New | Providing FHTC in school in Paitkapara PWSS under Alipurduar Division P.H.E Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000492/2022-2023 | 3356/ALD | 14/03/2023 | 13/04/2023 | HARIDAS GHOSH | 0.07 | 0 | 0 | 100
5 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | BARIGURI PIPED WATER SUPPLY SCHEME | SM/13246 | New | Providing FHTC in school in Banchukamari PWSS under Alipurduar Division P.H.E Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000493/2022-2023 | 3357/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.87 | 0 | 0 | 100
6 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | BARIGURI PIPED WATER SUPPLY SCHEME | SM/13246 | New | New Service Connection at Bairaguri P/H No.I |  |  | BILL/01685/2023-2024 | BP-2023-24-347 | 27/09/2023 |  | WBSEDCL | 7.58 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | BARIGURI PIPED WATER SUPPLY SCHEME | SM/13246 | New | New Service Connection at Bairaguri P/H No.II |  |  | BILL/01686/2023-2024 | BP-2023-24-348 | 27/09/2023 |  | WBSEDCL | 3.88 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | BARIGURI PIPED WATER SUPPLY SCHEME | SM/13246 | New | New Service Connection at Bairaguri P/H No.III |  |  | BILL/01687/2023-2024 | BP-2023-24-349 | 27/09/2023 |  | WBSEDCL | 6.08 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | BARIGURI PIPED WATER SUPPLY SCHEME | SM/13246 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bariguri water supply scheme, TW no I,II and III of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/001034/2023-2024 | 2664/NMD-II | 04/09/2023 | 04/10/2023 | A.S. ENTERPRISE | 27.56 | 0 | 0 | 0
Total | [13 empty] | 657.74 | 137.36 | 20.88