## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Supply of CIDF & CISS Pipes and specials for Kayakhata WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000240/2023-2024 | 1775/ALD | 28/08/2023 | 27/09/2023 | HARI CONSTRUCTION | 6.76 | 6.76 | 100 | 100
2 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Providing balance FHTC for KAYAKHATA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000242/2023-2024 | 1788/ALD | 29/08/2023 | 28/10/2023 | HARI CONSTRUCTION | 11.22 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Supply of CIPE Special & CI Jeffy Coupling for Kayakhata Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000480/2023-2024 | 698/ALD | 07/03/2024 | 06/04/2024 | HARI CONSTRUCTION | 15.33 | 6.87 | 44.8 | 85
4 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 200 cum OHR as per Departmental Design & drawing including soil investigation works, providing FHTC and others allied works for KAYAKHATA PWSS Under Alipurduar Division PHE DTE. (2nd call) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000514/2022-2023 | 3395/ALD | 16/03/2023 | 06/09/2024 | GOUTAM KUMAR DAS | 316.2 | 171.37 | 54.2 | 43
5 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 3048/ALD | 08/02/2023 |  | Resource Division | 29.21 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 140/ALD | 10/01/2024 |  | Resource Division | 9.76 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | NEW SERVICE CONNECTION CHARGE FOR KAYAKHATA PWSS PH NO -I |  |  | BILL/00053/2024-2025 | BP-13/24-25 | 08/04/2024 |  | WBSEDCL | 3.2 | 0 | 0 | null
8 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | New Service Connection Charges for Kayakhata PWSS PH NO-II |  |  | BILL/00986/2024-2025 | BP-282/24-25 | 20/08/2024 |  | WBSEDCL | 9.9 | 0 | 0 | null
9 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | KAYAKHATA PIPED WATER SUPPLY SCHEME | SM/13299 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Kayakhata Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/002506/2023-2024 | 2465/NMD-II | 11/08/2023 | 10/09/2023 | KAMAKHYA ENTERPRISE | 20.14 | 0 | 0 | 0
Total | [13 empty] | 421.73 | 185 | 43.87