## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 | New | Providing balance FHTC for MARAKHATA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000215/2023-2024 | 1569/ALD | 23/08/2023 | 22/09/2023 | HARI CONSTRUCTION | 4.69 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 | New | Supply of CIDF & CISS Pipes and specials for Marakhata WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000225/2023-2024 | 1598/ALD | 25/08/2023 | 24/09/2023 | HARI CONSTRUCTION | 6.76 | 6.76 | 99.98 | 100
3 | ALIPURDUAR | Kumargram | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 | New | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, Supply of DI pipe and specials, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at MARAKHATA HW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000369/2023-2024 | 85/ALD | 10/01/2024 | 06/10/2024 | HARIDAS GHOSH | 65.13 | 0 | 0 | 35
4 | ALIPURDUAR | Kumargram | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 | New | Constructions of P/H and T/W Boring by ODEX-165 Method of drilling at HW and 2nd site , LDS with UPVC P/L inclu. rising main and delivery connection, Cons. of 200 Cum OHR as per Departmental Design & drawing alongwith soil investigation, providing FHTC and others allied works for MARAKHATA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar RWS,Birpara Sub Division | ORD/000436/2022-2023 | 2863/ALD | 17/01/2023 | 06/01/2025 | HARIDAS GHOSH | 355.8 | 236.35 | 66.43 | 27
5 | ALIPURDUAR | Kumargram | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1475/ALD | 16/08/2023 |  | Resource Division | 29.72 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 | New | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 131/ALD | 10/01/2024 |  | Resource Division | 8.44 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MARAKHATA PWSS PH NO-I |  |  | BILL/00037/2023-2024 | BP-2023-24-15 | 27/04/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MARAKHATA PWSS PH NO-II |  |  | BILL/00038/2023-2024 | BP-2023-24-26 | 27/04/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 | New | ADDITIONAL QUOTATION FOR MARAKHATA PWSS PH NO-2 |  |  | BILL/00044/2024-2025 | BP-01/24-25 | 08/04/2024 |  | WBSEDCL | 4.3 | 0 | 0 | null
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MARAKHATA water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000696/2023-2024 | 2160/NMD-II | 27/07/2023 | 26/08/2023 | S.S ENTERPRISES | 19.12 | 8.73 | 45.65 | 100
Total | [13 empty] | 496.37 | 251.84 | 50.74