## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Providing FHTC from existing distribution system as per specification for Nimtijhora TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000264/2023-2024 | 1882/ALD | 07/09/2023 | 07/10/2023 | M/S A. B. ENTERPRISE | 7.09 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Laying of CIDI pipes & HDPE (PN-10) pipeline and other allied works for Nimtijhora Tea Garden PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000396/2023-2024 | 207/ALD | 16/01/2024 | 15/04/2024 | SAMIRON PODDER | 44.44 | 1.61 | 3.62 | 7
3 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 100 Cum OHR as per Departmental Design & drawing , TWO nos. pump house & boundary wall, providing FHTC, Soil Investigation work and others allied works for NIMTIJHORA TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE | HQ-A.E | Alipurduar Sub Division | ORD/000578/2022-2023 | 3639/ALD | 31/03/2023 | 27/09/2023 | SAMIRON PODDER | 207.36 | 88.57 | 42.71 | 90
4 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 2784/ALD | 18/12/2023 |  | Resource Division | 6.17 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | New Service connection charge for Nimti Jhora tea garden PWSS P/H No-I. |  |  | BILL/00561/2023-2024 | BP-2023-24-190 | 22/06/2023 |  | WBSEDCL | 1.36 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | New Service connection charge for Nimti Jhora tea garden PWSS P/H No-II |  |  | BILL/00562/2023-2024 | BP-2023-24-189 | 22/06/2023 |  | WBSEDCL | 1.36 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Nimtijhora TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000838/2023-2024 | 2413/NMD-II | 10/08/2023 | 09/09/2023 | SUNLIT | 18.75 | 0 | 0 | 90
Total | [13 empty] | 286.54 | 90.18 | 31.47