## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. | SM/15210 | Augmentation | Construction of 2nos pump house, boundary wall, TW boring by ODEX-195 method of drilling for Augmentation of Dhumchipara PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000389/2023-2024 | 200/ALD | 16/01/2024 | 15/05/2024 | MITHUN DAS | 54.27 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. | SM/15210 | Augmentation | Construction of boulder apron for Dhumchipara PWSS for protection of existing Pump house under Alipurduar Division. | Birpara A.E | Birpara Sub Division | ORD/000488/2023-2024 | 744/ALD | 12/03/2024 | 26/04/2024 | MANI PRADHAN | 3.59 | 1.42 | 39.63 | 50
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. | SM/15210 | Augmentation | Boring of TW, Construction of Pumphouse, Boundary wall, Laying of Distribution system for Augmentation of Dhumchipara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000502/2022-2023 | 3324/ALD | 13/03/2023 | 07/03/2024 | GIRIRAJ ENTERPRISE | 22.78 | 8.44 | 37.04 | 70
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. | SM/15210 | Augmentation | Replacement of damaged pipeline with HDPE and DI pipes for Dhumchipara PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/09896) | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000505/2023-2024 | 823/ALD | 14/03/2024 | 13/05/2024 | MONORAMA ENTERPRISE | 5.73 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. | SM/15210 | Augmentation | Nee Service Connection for Dhumchipara T.G PWSS |  |  | BILL/02302/2023-2024 | BP-2023-24-503 | 05/01/2024 |  | WBSEDCL | 6.73 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. | SM/15210 | Augmentation | Additional works in connection with yard lighting arrangement at Dalmore water supply scheme (Aug), P/H No. III under Northern Mechanical Division II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000080/2023-2024 | 147/AMSD | 06/07/2023 | 26/07/2023 | M/S P.P ELECTRICALS | 1.93 | 0 | 0 | 100
7 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DHUMCHIPARA TG PIPED WATER SUPPLY SCHEME. | SM/15210 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dhumchipara TG Water Supply Scheme TW No.- I under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000912/2023-2024 | 2468/NMD-II | 11/08/2023 | 10/09/2023 | M/S ANJALI ENTERPRISE | 14.86 | 5.41 | 36.43 | 50
Total | [13 empty] | 109.89 | 15.27 | 13.9