## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Land Development, repairing of Pump house, construction of Pathway and protection work of 3rd TW site of Narathali PWSS under Alipurduar Divn, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000334/2023-2024 | 2520/ALD | 24/11/2023 | 23/01/2024 | SREE MAA CONSTRUCTION | 6.99 | 2.46 | 35.26 | 100
2 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Repairing of HW site boundary wall (40M), construction of pathway, surface drain, chatal and other misc works related to Narathali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000338/2023-2024 | 2524/ALD | 24/11/2023 | 23/01/2024 | TAPAN CHANDA | 5.33 | 0 | 0 | 100
3 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at PURBA NARATHALI HW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000371/2023-2024 | 87/ALD | 10/01/2024 | 09/04/2024 | MADHAB SAHA | 34.86 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Supply of DI specials and CI Jeffy coupling for Purba Narathali Water Supply Scheme(SM/16537) of Kumargram Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000514/2023-2024 | 833/ALD | 14/03/2024 | 13/04/2024 | DILIP MAHATO | 13.51 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Constructions of pump house & Tube well Boring by ODEX-165 Method of drilling at HW site & 2nd site , laying of distribution system with UPVC pipeline including rising main & delivery connection, Constructions of 250 Cum OHR as per Departmental Design & drawing along with the Soil investigation works , providing FHTC and others allied works for Purba Narathali PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000550/2022-2023 | 3573ALD | 27/03/2023 | 21/03/2024 | MADHAB SAHA | 373.15 | 249.11 | 66.76 | 62
6 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 186/ALD | 28/04/2023 |  | Resource Division | 246.11 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Alipurduar Division | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 26/ALD | 10/01/2024 |  | Resource Division | 10.95 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PURBA NARTHALI PWSS PH NO-I |  |  | BILL/00035/2023-2024 | BP-2023-24-49 | 12/05/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PURBA NARTHALI PWSS PH NO-II |  |  | BILL/00036/2023-2024 | BP-2023-24-48 | 12/05/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | ADDITIONAL QUOTATION FOR PURBA NARARTHALI PH NO-I |  |  | BILL/00043/2024-2025 | BP-04/24-25 | 08/04/2024 |  | WBSEDCL | 2.27 | 0 | 0 | null
11 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | ADDITIONAL QUOTATION FOR PURBA NARARTHALI PH NO-2 |  |  | BILL/00045/2024-2025 | BP-05/24-25 | 08/04/2024 |  | WBSEDCL | 12.74 | 0 | 0 | null
12 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Purba Narthali Water Supply Scheme TW No.- I and,II under NMD-II,PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001046/2023-2024 | 2693/NMD-II | 14/09/2023 | 14/10/2023 | P K ENGINEERING | 21.75 | 0 | 0 | 0
Total | [13 empty] | 730.08 | 251.58 | 34.46