## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/16821 | New | Construction of tube wells (3 nos.) by Reverse rotary method of drilling Method of drilling at HW site, 2nd TW site and 3rd site, soil investigation at HW site, constructions of 100 Cum OHR at HW, construction of pump house and boundary wall at H/W, 2nd site and 3rd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Dalmoney Tea Garden PWSS (Zone-I & Zone-II) Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000574/2022-2023 | 3635/ALD | 31/03/2023 | 27/09/2023 | M/S HARI BHUSHAN GHOSH AND CO. | 202.87 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/16821 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1481/ALD | 16/08/2023 |  | Resource Division | 16.32 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/16821 | New | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 135/ALD | 10/01/2024 |  | Resource Division | 2.16 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/16821 | New | NEW SERVICE CONNECTION FOR DALMONI TG PWSS TW NO-I |  |  | BILL/03013/2023-2024 | BP-2023-24-690 | 14/03/2024 |  | WBSEDCL | 6.67 | 0 | 0 | null
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALMONI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/16821 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for DALMONI T.G water supply scheme, TW no I and II of ZONE-I AND TW NO.I OF ZONE-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000953/2023-2024 | 2559/NMD-II | 18/08/2023 | 17/09/2023 | B.B CONCERNED | 31.29 | 10.45 | 33.41 | 45
Total | [13 empty] | 259.31 | 10.45 | 4.03