## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000049/2023-2024 | 395/ALD | 19/05/2023 | 16/09/2023 | TAPASH KUMAR BHOWMICK | 4.29 | 2.15 | 50 | 20
2 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | "Supply of DIDF Special and CI Jeffy Coupling for Dalgaon TG Water Supply Scheme(SM/16823) of Falakata Block under Alipurduar Division P.H.E. Dte. " | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000527/2023-2024 | 846/ALD | 14/03/2024 | 13/04/2024 | MADHAB SAHA | 16.41 | 8.2 | 50 | 62
3 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , constructions of 200 Cum OHR at HW including soil investigation , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Dalgaon Tea Garden PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar RWS,Birpara Sub Division | ORD/000573/2022-2023 | 3634/ALD | 31/03/2023 | 27/09/2023 | M/S MRITYUNJAY PAUL AND SONS | 390.34 | 131.56 | 33.71 | 51
4 | ALIPURDUAR | Falakata | Alipurduar Division | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1954/ALD | 12/09/2023 |  | Resource Division | 40.05 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | NEW SERIVICE CONNECTION CHARGES FOR DALGAON TG PWSS TW NO-I |  |  | BILL/03010/2023-2024 | BP-2023-24-687 | 14/03/2024 |  | WBSEDCL | 21.42 | 0 | 0 | null
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | NEW SERVICE CONNECTION CHARGE FOR DALGAON TG P/H NO-II |  |  | BILL/03015/2023-2024 | BP-2023-24-692 | 14/03/2024 |  | WBSEDCL | 4.69 | 0 | 0 | null
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 | New | Supply, delivery, installation, commissioning andtrial run of electro-mechanical components alongwith Cu wound line voltage corrector forRejuvenation of DALGAON T.G water supplyscheme, TW no I AND II underJJM under NMD II,PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000935/2023-2024 | 2544/NMD-II | 16/08/2023 | 15/09/2023 | M/S MATRI CONSTRUCTION | 21.85 | 0 | 0 | 0
Total | [13 empty] | 499.05 | 141.91 | 28.44