## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 |  | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
2 | ALIPURDUAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 5.19 | 50 | 100
3 | ALIPURDUAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 0 | 0 | 95
4 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 |  | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
5 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 |  | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
6 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 |  | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
7 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 |  | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
8 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
9 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 1.68 | 49.01 | 100
10 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
11 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 0
Total | [13 empty] | 373.07 | 16.84 | 4.51