## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas under Jalpaiguri District. Block - Maynaguri. | Assistant Engineer | Junior Engineer | ORD/000012/2022-2023 | 948/JD | 19/04/2022 | 03/06/2022 | VENKATESHWARA ENTERPRISES | 44.24 | 41.87 | 94.65 | 0
2 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas under Jalpaiguri District. Block-Dhupguri. | Assistant Engineer | Junior Engineer | ORD/000014/2022-2023 | 956/JD | 19/04/2022 | 03/06/2022 | RADIANT | 50.8 | 39.5 | 77.76 | 0
3 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparetion of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas under Jalpaiguri District. Block - Mal | Assistant Engineer | Junior Engineer | ORD/000044/2022-2023 | 904/JD | 07/04/2022 | 22/05/2022 | M/S RUDRABHISHEK ENTERPRISES PVT. LTD. | 83.11 | 63.29 | 76.15 | 50
4 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas of SALUGARA under Jalpaiguri District. Block - Rajganj. Considering two Zones. | Assistant Engineer,HQ | Junior Engineer | ORD/000156/2022-2023 | 1515/JD | 29/07/2022 | 13/08/2022 | SUBHANKAR GHOSH | 2.62 | 2.62 | 100 | 100
5 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas of SAMARNAGAR under Jalpaiguri District. Block - Rajganj. | Assistant Engineer,HQ | Junior Engineer | ORD/000157/2022-2023 | 1514/JD | 29/07/2022 | 13/08/2022 | SUBHANKAR GHOSH | 1.89 | 1.89 | 100 | 100
6 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas of NOAPARA under Jalpaiguri District. Block - Rajganj. | Assistant Engineer,HQ | Junior Engineer | ORD/000158/2022-2023 | 1513/JD | 27/07/2022 | 11/08/2022 | SUBHANKAR GHOSH | 2.84 | 2.84 | 100 | 100
7 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas at different Blocks within Jalpaiguri. Distcit under Jalpaiguri Division, P.H.E. Dte. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000197/2022-2023 | 1738/JD | 08/09/2022 | 03/10/2022 | RADIANT | 9.59 | 9.83 | 102.48 | 0
8 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas at different Blocks within Jalpaiguri. Distcit under Jalpaiguri Division, P.H.E. Dte. (Part-A) |  |  | ORD/000231/2022-2023 | 1748/JD | 08/09/2022 | 03/10/2022 | SAMARTH INFRA TECH SERVICES PRIVATE LIMITED | 9.59 | 9.27 | 96.72 | 0
9 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas at different Blocks within Jalpaiguri. Distcit under Jalpaiguri Division, P.H.E. Dte. (Part-B) | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000237/2022-2023 | 1750/JD | 09/09/2022 | 04/10/2022 | SAMARTH INFRA TECH SERVICES PRIVATE LIMITED | 9.59 | 0 | 0 | 0
10 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Continuation Order of "Preparation of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas at different Blocks within Jalpaiguri. District under Jalpaiguri Division, P.H.E. Dte. (Part-D)" | Assistant Engineer | Junior Engineer | ORD/000309/2022-2023 | 1837/JD | 15/09/2022 | 29/09/2022 | RADIANT | 2.4 | 2.23 | 93.04 | 100
11 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation and supply of geo refference drawing (CAD-GIS) / layout of plan of the zone wise command area of water distribution and transmission network under Simulguri PWSS at Block- Rajganj under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000459/2022-2023 | 1923/JD | 28/09/2022 | 05/10/2022 | SAMARTH INFRA TECH SERVICES PRIVATE LIMITED | 0.74 | 0.74 | 100 | 0
12 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation and supply of geo refference drawing (CAD-GIS) / layout of plan of the zone wise command area of water distribution and transmission network under Panikauri PWSS at Block- Rajganj under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000460/2022-2023 | 1929/JD | 29/09/2022 | 06/10/2022 | SAMARTH INFRA TECH SERVICES PRIVATE LIMITED | 0.74 | 0.74 | 100 | 0
13 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation and supply of geo refference drawing (CAD-GIS) / layout of plan of the zone wise command area of water distribution and transmission network under Neora Majhiali PWSS at Block- Matiali under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000461/2022-2023 | 1935/JD | 29/09/2022 | 06/10/2022 | SAMARTH INFRA TECH SERVICES PRIVATE LIMITED | 0.74 | 0.74 | 100 | 0
14 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation and supply of geo refference drawing (CAD-GIS) / layout of plan of the zone wise command area of water distribution and transmission network under Kurti TG PWSS at Block- Nagrakata under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000462/2022-2023 | 1936/JD | 29/09/2022 | 06/10/2022 | SAMARTH INFRA TECH SERVICES PRIVATE LIMITED | 0.74 | 0.74 | 100 | 0
15 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation and supply of geo refference drawing (CAD-GIS) / layout of plan of the zone wise command area of water distribution and transmission network under Hridaypur PWSS & Dhumpara PWSS at Block- Nagrakata under Jalpaiguri Division, PHE Dte. |  |  | ORD/000463/2022-2023 | 1937/JD | 29/09/2022 | 06/10/2022 | SAMARTH INFRA TECH SERVICES PRIVATE LIMITED | 0.74 | 0.74 | 100 | 0
16 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation and supply of geo refference drawing (CAD-GIS) / layout of plan of the zone wise command area of water distribution and transmission network under Mahanbhita PWSS at Block- Rajganj under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000464/2022-2023 | 1938/JD | 29/09/2022 | 06/10/2022 | SAMARTH INFRA TECH SERVICES PRIVATE LIMITED | 0.37 | 0.37 | 100 | 0
17 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparetion of Detailed Project Reports for Implementation of New Piped Water Supply Scheme for uncovered areas under Jalpaiguri District. Block - Rajganj, Matili, Nagrakata) | Assistant Engineer | Junior Engineer | ORD/000732/2021-2022 | 949/JD | 31/03/2022 | 15/05/2022 | M/S SAMARTH INFRA TECH SERVICES PRIVATE LIMITED | 43.3 | 9.26 | 21.39 | 0
18 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of GEO reference drawing and DPR booklet in connection with preparation of DPR for Rejuvenation of Dabgram-II piped water sully scheme in connection with FHTC connection under "JAL SWAPNO " under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000894/2021-2022 | 65/JD | 06/01/2022 | 13/01/2022 | SUBHANKAR GHOSH | 1.8 | 1.8 | 100 | 100
19 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | PREPARATION PF DPR FOR BHORAM COB DIVN. |  |  | BILL/00593/2022-2023 | BP-532-2022-23 | 03/01/2023 | 03/01/2023 | M/S BADAL CH SAHA | 3.15 | 0 | 0 | 0
20 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | HIRING VEWHICLE FOR AE HQ |  |  | BILL/00596/2024-2025 | BP-231 | 01/08/2024 | 01/08/2024 | BHAGWATI BHUJEL | 0.77 | 0 | 0 | 0
21 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | SUPPLY CANON 1IR PHOTO MACHINE AT COB DIVISIONAL OFFICE |  |  | BILL/00683/2022-2023 | BP-761-22-23-P1 | 08/03/2023 | 08/03/2023 | ELECTRO SERVICES PVT.LTD | 1.45 | 0 | 0 | 0
22 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | EXECUTION OF DIFFERENT WORK AT CHEKIACHARA PWSS |  |  | BILL/02017/2023-2024 | BP-1405 | 31/03/2024 | 31/03/2024 | KAJAL KUMAR DE | 6.56 | 0 | 0 | 0
23 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
24 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of BARAKODALI (Zone-II) Piped Water Supply Scheme under TUFANGANJ Sub-division of Cooch Behar Division, P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000159/2022-2023 | 618/CD | 16/08/2022 | 05/09/2022 | RADIANT | 2.69 | 2.69 | 100 | 1
25 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of SITALKUCHI (Zone-II) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000160/2022-2023 | 619/CD | 16/08/2022 | 05/09/2022 | RADIANT | 3.01 | 3.01 | 100 | 1
26 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of SITALKUCHI (Zone-III) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000161/2022-2023 | 620/CD | 16/08/2022 | 05/09/2022 | RADIANT | 3.41 | 3.27 | 95.82 | 1
27 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of SITALKUCHI (Zone-IV) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000162/2022-2023 | 621/CD | 16/08/2022 | 05/09/2022 | RADIANT | 3.41 | 3.2 | 93.65 | 1
28 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of PUTIA BARAMASIA (Zone-II) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000165/2022-2023 | 624/CD | 16/08/2022 | 05/09/2022 | RADIANT | 3.08 | 2.99 | 96.85 | 0
29 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of HEMKUMARI (Zone-III) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000170/2022-2023 | 629/CD | 16/08/2022 | 05/09/2022 | RADIANT | 2.99 | 2.99 | 100 | 0
30 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of DAKSHIN BASARAJBALA (Zone-II) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000171/2022-2023 | 630/CD | 16/08/2022 | 05/09/2022 | RADIANT | 2.78 | 2.78 | 100 | 0
31 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of BAJEJAMA CHILAKHANA (Zone-III) Piped Water Supply Scheme under TUFANGANJ Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000173/2022-2023 | 632/CD | 16/08/2022 | 05/09/2022 | RADIANT | 2.88 | 2.88 | 100 | 1
32 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Bhulki Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division, P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000288/2021-2022 | 1003/CD | 10/01/2022 | 30/01/2022 | RADIANT | 2.82 | 2.82 | 100 | 1
33 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Baskotal Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000289/2021-2022 | 1004/CD | 10/01/2022 | 30/01/2022 | RADIANT | 2.68 | 2.59 | 96.63 | 1
34 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of SITALKUCHI Piped Water Supply Scheme under Mathabhanga Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000291/2021-2022 | 1006/CD | 10/01/2022 | 30/01/2022 | RADIANT | 4.16 | 3.57 | 85.91 | 1
35 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Upenchaukikuchlibari Piped Water Supply Scheme under Mathabhanga Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000295/2021-2022 | 1010/CD | 10/01/2022 | 30/01/2022 | RADIANT | 2.61 | 2.61 | 100 | 0
36 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Putia Bara Masia Piped Water Supply Scheme under Mathabhanga Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000296/2021-2022 | 1011/CD | 10/01/2022 | 30/01/2022 | RADIANT | 3.17 | 3.17 | 100 | 0
37 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Chilkirhat Piped Water Supply Scheme under Cooch behar sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000297/2021-2022 | 1012/CD | 10/01/2022 | 30/01/2022 | RADIANT | 2.82 | 2.82 | 100 | 1
38 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Khattimari Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000303/2021-2022 | 1018/CD | 10/01/2022 | 30/01/2022 | RADIANT | 3.31 | 3.13 | 94.5 | 1
39 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Hemkumari Piped Water Supply Scheme under Mathabhanga Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000305/2021-2022 | 1020/CD | 10/01/2022 | 30/01/2022 | RADIANT | 2.85 | 2.85 | 100 | 0
40 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Dakshin Basarajbala Piped Water Supply Scheme under Mathabhanga Sub-division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000306/2021-2022 | 1021/CD | 10/01/2022 | 30/01/2022 | RADIANT | 2.89 | 2.89 | 100 | 0
41 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Bajejama Chilakhana Piped Water Supply Scheme under Tufanganj Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000307/2021-2022 | 1022/CD | 10/01/2022 | 30/01/2022 | RADIANT | 3.1 | 3.1 | 100 | 1
42 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Bararangras Piped Water Supply Scheme under Cooch Behar Sadar Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000554/2021-2022 | 1538/CD | 17/03/2022 | 06/04/2022 | M/S BADAL CH SAHA | 3.15 | 3.15 | 100 | 0
43 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Chandan Chowra Piped Water Supply Scheme under Cooch Behar Sadar Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000555/2021-2022 | 1539/CD | 17/03/2022 | 06/04/2022 | M/S BADAL CH SAHA | 3.02 | 3.02 | 100 | 0
44 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Sajherpar Ghoramara Piped Water Supply Scheme under Cooch Behar Sadar Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000556/2021-2022 | 1540/CD | 17/03/2022 | 06/04/2022 | M/S BADAL CH SAHA | 3.02 | 3.02 | 100 | 0
45 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Bhoram Piped Water Supply Scheme under Cooch Behar Sadar Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000557/2021-2022 | 1541/CD | 17/03/2022 | 06/04/2022 | M/S BADAL CH SAHA | 3.15 | 0 | 0 | 0
46 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Bhutkura Piped Water Supply Scheme under Cooch Behar Sadar Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000558/2021-2022 | 1542/CD | 17/03/2022 | 06/04/2022 | M/S BADAL CH SAHA | 3.02 | 2.98 | 98.69 | 0
47 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Kharija Baladanga Piped Water Supply Scheme under Cooch Behar Sadar Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000559/2021-2022 | 1543/CD | 17/03/2022 | 06/04/2022 | M/S BADAL CH SAHA | 3.02 | 2.78 | 92.16 | 0
48 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Ruier Khuthi Piped Water Supply Scheme under Cooch Behar Sadar Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000560/2021-2022 | 1544/CD | 17/03/2022 | 06/04/2022 | M/S BADAL CH SAHA | 3.02 | 2.94 | 97.39 | 0
49 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Gabua Piped Water Supply Scheme under Cooch Behar Sadar Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000561/2021-2022 | 1546/CD | 17/03/2022 | 06/04/2022 | M/S BADAL CH SAHA | 3.02 | 3.01 | 99.56 | 0
50 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Falimari Piped Water Supply Scheme under Tufanganj Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000562/2021-2022 | 1545/CD | 17/03/2022 | 06/04/2022 | M/S BADAL CH SAHA | 3.02 | 3.02 | 100 | 0
51 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Bara Adabari Piped Water Supply Scheme under Cooch Behar Sadar Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000563/2021-2022 | 1547/CD | 17/03/2022 | 06/04/2022 | M/S BADAL CH SAHA | 3.02 | 2.78 | 92.16 | 0
52 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Balasi Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000564/2021-2022 | 1386/CD | 04/03/2022 | 24/03/2022 | M/S SOBHA & CO. | 3.02 | 3.02 | 100 | 0
53 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Dakshin Alokjhari Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000565/2021-2022 | 1532/CD | 15/03/2022 | 04/04/2022 | M/S SOBHA & CO. | 3.02 | 2.76 | 91.6 | 0
54 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Jorpatki Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000566/2021-2022 | 1383/CD | 03/03/2022 | 23/03/2022 | M/S SOBHA & CO. | 3.15 | 3.15 | 100 | 0
55 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Sarhati Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000567/2021-2022 | 1482/CD | 11/03/2022 | 31/03/2022 | M/S SOBHA & CO. | 3.02 | 2.55 | 84.59 | 0
56 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Angarkata Paradubi Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000571/2021-2022 | 1387/CD | 04/03/2022 | 24/03/2022 | M/S SOBHA & CO. | 3.15 | 0 | 0 | 0
57 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Balasundar Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000572/2021-2022 | 1409/CD | 08/03/2022 | 28/03/2022 | M/S SOBHA & CO. | 3.02 | 2.74 | 91.01 | 0
58 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Unish Basa Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000573/2021-2022 | 1397/CD | 04/03/2022 | 24/03/2022 | M/S SOBHA & CO. | 3.02 | 3.02 | 100 | 0
59 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Debottar Bakshiganj Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000574/2021-2022 | 1537/CD | 17/03/2022 | 06/04/2022 | M/S SOBHA & CO. | 3.02 | 2.33 | 77.39 | 0
60 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Bara Saulmari Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000759/2022-2023 | 1474/CD | 10/03/2023 | 30/03/2023 | M/S SOBHA & CO. | 3.02 | 2.85 | 94.45 | 0
61 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Sitalkuchi Zone-V Piped Water Supply Scheme under Mathabhanga Sub-Division of Cooch Behar Division, PHED. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000806/2022-2023 | 836/CD | 14/09/2022 | 21/09/2022 | RADIANT | 0.99 | 0 | 0 | 0
62 | ALIPURDUAR |  | Coochbehar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR for Augmentation of Santoshpur Piped Water Supply Scheme under Tufanganj Sub-Division of Cooch Behar Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000807/2022-2023 | 837/CD | 14/09/2022 | 21/09/2022 | RADIANT | 0.99 | 0 | 0 | 0
63 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Augumentation D.P.R after investigation for Kalaberia, Prodhanpara, Naothoartari, Bariguri, Dakshin Barajhar Forest W/S scheme under Alipurduar-I Block under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000171/2022-2023 | 1065/ALD | 26/07/2022 | 25/08/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD | 12.02 | 12.02 | 100 | 100
64 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Augmentation D.P.R after investigation For Chengpara, Kayakhata, Uttar Shibkata, Uttar Majidkhana, Dakshin Majidkhana, Purba Chikliguri, Nurpur, W/S scheme under Alipurduar-II Block under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000172/2022-2023 | 1066/ALD | 26/07/2022 | 25/08/2022 | RADIANT | 16.83 | 16.83 | 100 | 0
65 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Augmentation D.P.R after investigation For Narasingpur, Dhanirampur, Malsagaon, Benkanti, Uttar Deogaon, paschim Deogaon, Mairadanga, Lachmandabri, Umacharanpur, W/S scheme under Falakata Block under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E | Birpara Sub Division | ORD/000173/2022-2023 | 1067/ALD | 26/07/2022 | 25/08/2022 | NSS ASSOCIATES CONSULTING ENGINEERS & INFRA PVT.LTD | 20.8 | 18.55 | 89.19 | 0
66 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Augmentation D.P.R after investigation For Paschim Satali, Uttar Mendabari, Nimti Domohani, Buxa Forest (Rajabhatkhawa), W/S scheme under Kalchini Block under Alipurduar Division PHE Dte. | HQ-A.E |  | ORD/000174/2022-2023 | 1068/ALD | 26/07/2022 | 25/08/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD | 9.61 | 9.61 | 100 | 0
67 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Augmentation D.P.R after investigation For Madhya Kamakhyaguri, Telipara (Zone-I), Telipara (Zone-II), Chota Daldali, Uttar Narathali, Baruipara(Zone-I), Baruipara(Zone-II) W/S scheme under Kumargram Block under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000175/2022-2023 | 1069/ALD | 26/07/2022 | 25/08/2022 | RADIANT | 16.83 | 16.83 | 100 | 0
68 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of Augmentation D.P.R after investigation For Sishujhumra and Madhya Khairbari W/S scheme under Madarihat-Birpara Block under Alipurduar Division PHE Dte. | Birpara A.E |  | ORD/000176/2022-2023 | 1070/ALD | 26/07/2022 | 25/08/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD | 5.2 | 5.2 | 100 | 0
69 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of D.P.R after investigation For Kadambini W/S scheme under Falakata Block under Alipurduar Division PHE Dte. | Birpara A.E |  | ORD/000203/2022-2023 | 1189/ALD | 05/08/2022 | 04/09/2022 | ANIK BHATTACHARJEE | 2.34 | 2.34 | 100 | 0
70 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of D.P.R after investigation For Ethelbari W/S scheme under Falakata Block under Alipurduar Division PHE Dte. | Birpara A.E |  | ORD/000204/2022-2023 | 1190/ALD | 05/08/2022 | 04/09/2022 | ANIK BHATTACHARJEE | 2.47 | 2.47 | 100 | 0
71 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR after investigation for Foskadanga, Pararpar, Torsha Forest Piped Water Supply Scheme under Alipurduar-I Block, Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000248/2022-2023 | 1390/ALD | 29/08/2022 | 28/09/2022 | M/S BADAL CHANDRA SAHA | 6.82 | 6.82 | 100 | 0
72 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR after investigation for Paschim Khalishamari, Brajerkuthi Piped Water Supply Scheme under Alipurduar-II Block, Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000249/2022-2023 | 1391/ALD | 29/08/2022 | 28/09/2022 | RADIANT | 4.43 | 4.43 | 100 | 0
73 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR after investigation for Nimtijhora Tea Garden, Beech Tea Garden, Rangamati Tea Garden, Bhatpara Tea Garden and Bhatkhawa Tea Garden Piped Water Supply Scheme under Kalchini Block, Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000250/2022-2023 | 1393/ALD | 29/08/2022 | 28/09/2022 | SAMARTH INFRA TECH SERVICES PVT. LTD | 11.31 | 11.31 | 100 | 0
74 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR after investigation for Dakshin Rangalibazna, Uttar Rangalibazna, Ballalguri and Garochira Bandapani Piped Water Supply Scheme under Madarihat-Birpara Block, Alipurduar Division, PHE Dte | Birpara A.E |  | ORD/000252/2022-2023 | 1394/ALD | 29/08/2022 | 28/09/2022 | M/S BADAL CHANDRA SAHA | 9.09 | 9.09 | 100 | 0
75 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR after investigation for Atiabari Tea Garden, Rajabhat Tea Garden, Buxa Hill Forest, Buxa Forest (Panbari Khanda) and Uttar Barajhar Forest Piped Water Supply Scheme under Kalchini Block, Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000253/2022-2023 | 1395/ALD | 29/08/2022 | 28/09/2022 | RADIANT | 11.08 | 0 | 0 | 0
76 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR after investigation for Paschim Chengmari and Jayanti Tea Garden II Piped Water Supply Scheme under Kumargram Block, Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000254/2022-2023 | 1396/ALD | 29/08/2022 | 28/09/2022 | M/S BADAL CHANDRA SAHA | 4.55 | 4.55 | 100 | 0
77 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of new DPR after investigation for Gangutia and Bhutia Forest Basti PWSS under Kalchini Blockunder Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000364/2023-2024 | 80/ALD | 10/01/2024 | 09/02/2024 | ANIK BHATTACHARJEE | 1.92 | 0 | 0 | 0
78 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of New DPR after investigation for PARMALANGI Piped Water Supply Scheme under Kalchini Block, Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000372/2023-2024 | 88/ALD | 10/01/2024 | 09/02/2024 | ANIK BHATTACHARJEE | 1.87 | 0 | 0 | 0
79 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of new DPR after investigation for Dalbadal Busty PWSS under Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000390/2023-2024 | 201/ALD | 16/01/2024 | 15/02/2024 | ANIK BHATTACHARJEE | 1.04 | 0 | 0 | 0
80 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of new DPR after investigation for Kalkut PWSS under Kalchini Block under Alipurduar Division, PHE Dte. |  |  | ORD/000400/2023-2024 | 211/ALD | 16/01/2024 | 15/02/2024 | ANIK BHATTACHARJEE | 1.91 | 0 | 0 | 0
81 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of detailed D.P.R. booklets in connection to Dhumchipara TG PWSS under Madarihat-Birpara Block under Alipurduar Division P.H.E Dte. | Birpara A.E |  | ORD/000419/2022-2023 | 2822/ALD | 11/01/2023 | 10/02/2023 | ANIK BHATTACHARJEE | 0.97 | 0.97 | 100 | 0
82 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of detailed D.P.R. booklets in connection to Hantupara PWSS under Madarihat-Birpara Block under Alipurduar Division P.H.E Dte. | Birpara A.E |  | ORD/000420/2022-2023 | 2823/ALD | 11/01/2023 | 10/02/2023 | ANIK BHATTACHARJEE | 0.97 | 0.97 | 100 | 0
83 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of detailed D.P.R. booklets in connection to Gargenda TG PWSS under Madarihat-Birpara Block under Alipurduar Division P.H.E Dte. | Birpara A.E |  | ORD/000421/2022-2023 | 2824/ALD | 11/01/2023 | 10/02/2023 | ANIK BHATTACHARJEE | 0.97 | 0.97 | 100 | 0
84 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR after investigation for DHANTALI, DAKSHIN CHENGMARI, PURBA MAJHERDABRI TG, UTTAR DHALKAR PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000490/2022-2023 | 3322/ALD | 13/03/2023 | 12/04/2023 | M/S BADAL CHANDRA SAHA | 7.92 | 7.92 | 100 | 0
85 | ALIPURDUAR |  | Alipurduar Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Jalpaiguri, Alipurduar and Coochbehar District in West Bengal. | SM/11505 | Support-M&E | Preparation of DPR after investigation for KHAGENHAT, PARPATLAKHAWA, MALANGI TG (PARAMALANGI) & BHUTRI FOREST PWSS UNDER Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000491/2022-2023 | 3323/ALD | 13/03/2023 | 12/04/2023 | M/S BADAL CHANDRA SAHA | 7.92 | 7.92 | 100 | 0
Total | [13 empty] | 606.84 | 429.75 | 70.82