## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | SM/07060 | Retrofitting | Providing House connection and extension of pipe line for Silbarihat area within PATLAKHAWA PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000072/2021-2022 | 879/ALD | 03/09/2021 | 02/11/2021 | TAPASH KUMAR BHOWMICK | 45.7 | 0 | 0 | 76.33
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | SM/07060 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block | ORD/000079/2021-2022 | 877/ALD | 03/09/2021 | 02/11/2021 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 0 | 73.2
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | SM/07060 | Retrofitting | Providing House connection for BAROBISHA ZONE- I water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000142/2020-2021 | 858/ALD | 14/10/2020 | 13/11/2020 | TAPAN CHANDA | 4.98 | 4.98 | 100 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | SM/07060 | Retrofitting | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | Alipurduar RWS | Birpara Sub Division | ORD/000183/2020-2021 | 1008/ALD | 12/11/2020 | 11/01/2021 | JAI BHARAT COMMERCIAL CORPORATION | 14.4 | 4.5 | 31.25 | 100
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | SM/07060 | Retrofitting | Providing House connection for PATLAKHAWA water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte. Part-IV | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000221/2020-2021 | 1172/ALD | 15/12/2020 | 13/02/2021 | SOUVIK ROY PALADHI | 23.92 | 0 | 0 | 79
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | SM/07060 | Retrofitting | Providing House connection for PURBA KATHALBARI water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar RWS | Birpara Sub Division | ORD/000222/2020-2021 | 1173/ALD | 15/12/2020 | 13/02/2021 | MADHAB SAHA | 19.93 | 5.98 | 30 | 0
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | SM/07060 | Retrofitting | Laying of DI pipeline, painting, plastering, land development and other misc works related to Patlakhawa OHR under Patlakhawa PWSS at Alipurduar-I Block, under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000286/2021-2022 | 1855/ALD | 13/12/2021 | 27/01/2022 | TAPAN CHANDA | 4.26 | 0 | 0 | 77
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | SM/07060 | Retrofitting | Construction of boulder apron and land development at Patlakhawa WSS (Pump House no-2) under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000296/2020-2021 | 1339/ALD | 11/01/2021 | 10/02/2021 | SHIBA ENTERPRISE | 4.98 | 4.98 | 99.84 | 0
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Patlakhawa Piped Water Supply Scheme (Phase-1) | SM/07060 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Silbarihat under Patlakhawa PWSS. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000468/2021-2022 | 2766/ALD | 25/02/2022 | 26/04/2022 | TAPASH KUMAR BHOWMICK | 42.34 | 0 | 0 | 74.67
Total | [13 empty] | 193.94 | 20.44 | 10.54