## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | SM/07128 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Simlabari area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block | ORD/000078/2021-2022 | 876/ALD | 03/09/2021 | 02/11/2021 | M/S AMIT KUMAR GUPTA | 35.43 | 0 | 0 | 75.2
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | SM/07128 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block | ORD/000079/2021-2022 | 877/ALD | 03/09/2021 | 02/11/2021 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 0 | 73.2
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | SM/07128 | Retrofitting | Withdrawing and relaying of UPVC and DI pipeline due to damaged during bitumen road construction and other misc works at Tapshikhata PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000146/2020-2021 | 941/ALD | 19/10/2020 | 18/12/2020 | KAMALESH ROY | 10.81 | 0 | 0 | 76.5
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | SM/07128 | Retrofitting | Providing extension of distribution line, AT TAPSHIKATHA G.P from the commissioned TAPSHIKATHA PWSS (UID-APD-022) UNDER ALIPURDUAR DIVISION PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000308/2020-2021 | 1481/ALD | 27/01/2021 | 28/03/2021 | KAMALESH ROY | 12.16 | 2.26 | 18.55 | 75.5
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | SM/07128 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of TAPSHIKHATA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000321/2021-2022 | 2197/ALD | 11/01/2022 | 11/04/2022 | DEBABRATA DUTTA | 21.58 | 4.43 | 20.52 | 68.67
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | SM/07128 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-6 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000350/2021-2022 | 2143/ALD | 06/01/2022 | 05/02/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 5.03 | 0 | 0 | 76
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | SM/07128 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of North side of Pukuritola area under Tapshikatha PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000369/2021-2022 | 2292/ALD | 24/01/2022 | 25/03/2022 | DEBAJYOTI SUTRADHAR | 26.52 | 24.9 | 93.88 | 77.5
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Tapshikatha Piped Water Supply Scheme (Phase-2) | SM/07128 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Tapshikhata PWSS Under Alipurduar Division, PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000442/2021-2022 | 2750/ALD | 24/02/2022 | 25/04/2022 | AMBITIOUS ENTERPRISE | 36.94 | 0 | 0 | 68
Total | [13 empty] | 181.89 | 31.59 | 17.37