## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme | SM/07131 | Retrofitting | Providing House connection for DHEKLAPARA PWSS at MADARIHAT-BIRPARA Block under Alipurduar Division PHED PART 1 | Birpara A.E | Birpara Sub Division | ORD/000082/2020-2021 | 634/ALD | 03/09/2020 | 02/12/2020 | DILIP MAHATO | 21.8 | 7.46 | 34.22 | 0
2 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme | SM/07131 | Retrofitting | Preparation of Augmentation D.P.R after investigation For Jateswar W/S scheme under Alipurduar Division. | Birpara A.E | Birpara Sub Division | ORD/000111/2021-2022 | 914/ALD | 06/09/2021 | 06/10/2021 | BHAGWATI BHUJEL | 2.31 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme | SM/07131 | Retrofitting | Laying of HDPE/DI pipe line at different area of flank of Dheklapara Bandapani under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000180/2020-2021 | 1005/ALD | 12/11/2020 | 11/01/2021 | M/S PALIT ENTERPRISE | 11.75 | 23.92 | 203.64 | 48
4 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme | SM/07131 | Retrofitting | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | Alipurduar RWS | Birpara Sub Division | ORD/000184/2020-2021 | 1009/ALD | 12/11/2020 | 11/01/2021 | M/S PALIT ENTERPRISE | 14.4 | 4.48 | 31.09 | 70
5 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme | SM/07131 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
6 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme | SM/07131 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHEKLAPARA T.G. Piped Water Supply Scheme | SM/07131 | Retrofitting | Fuel bill for the month of August 2021 |  |  | VCH/000569/2021-2022 | 120/21-22/PFMS | 08/09/2021 |  | SHIVAM SERVICE STATION | 0.18 | 0 | 0 | 0
Total | [13 empty] | 3143.67 | 35.86 | 1.14