## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) | SM/07181 | Retrofitting | Laying Delivary line with M.S FOR Connection of KAIJALI BUSTY WSS under Jainti TG Water Supply Scheme . | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000087/2022-2023 | 451/ALD | 13/05/2022 | 12/06/2022 | TAPASH KUMAR BHOWMICK | 4.94 | 4.86 | 98.44 | 66
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) | SM/07181 | Retrofitting | Providing House connection for KAIJALI BASTYI water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000150/2020-2021 | 862/ALD | 14/10/2020 | 13/11/2020 | DAS ENTERPRISE | 4.96 | 4.96 | 100 | 68
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) | SM/07181 | Retrofitting | Providing House connection for KAIJALI BUSTY water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000169/2020-2021 | 913/ALD | 16/10/2020 | 15/11/2020 | DAS ENTERPRISE | 4.96 | 4.96 | 100 | 66.5
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) | SM/07181 | Retrofitting | Providing House connection for KAIJALI BUSTY water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000210/2020-2021 | 1164/ALD | 15/12/2020 | 13/02/2021 | GHOSH & SAHA CONSTRUCTION | 19.93 | 14.95 | 75 | 68
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) | SM/07181 | Retrofitting | Restoration of pipe line for Turturi Khanda (Kaijali Busty Area), Culvert crossing and Laying Delivery line with DI and MS under Kaijali Busty TG WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000329/2021-2022 | 2202/ALD | 11/01/2022 | 12/03/2022 | TAPASH KUMAR BHOWMICK | 41.95 | 23.12 | 55.1 | 65.5
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-1) | SM/07181 | Retrofitting | Laying of distribution of HDPE/DI pipeline for TURTURI TG area, Kaijali Busty PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000480/2021-2022 | 2899/ALD | 08/03/2022 | 07/05/2022 | ASHOK SAPKOTA | 34.24 | 32.92 | 96.16 | 68
Total | [13 empty] | 110.99 | 85.78 | 77.28