## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Construction of Guard Wall in both side of drain infront of Alipurduar PHE Office |  |  | ORD/000134/2018-2019 | 217/ALD | 26/02/2019 |  | AKANSHA COMMERCIAL PRIVATE LTD. | 4.62 | 1.16 | 25.05 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Providing House connection for CHANDIRJHAR water supply scheme at ALIPURDUAR-II Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000165/2020-2021 | 909/ALD | 16/10/2020 | 15/11/2020 | SREE MAA CONSTRUCTION & CO. | 4.98 | 4.98 | 100 | 0
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Providing House connection and construction of different dia. sluice valve chamber including supply of CI materials for Jashodanga WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000192/2021-2022 | 1316/ALD | 05/10/2021 | 19/11/2021 | HARI CONSTRUCTION | 12.88 | 12.83 | 99.58 | 99
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Providing House connection for Jashodanga water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000205/2020-2021 | 1159/ALD | 15/12/2020 | 13/02/2021 | TAPASH KUMAR BHOWMICK | 29.89 | 17.18 | 57.47 | 98
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under JHOSHODANGA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000272/2020-2021 | 1284/ALD | 05/01/2021 | 06/03/2021 | MADHAB SAHA | 24.66 | 22.54 | 91.41 | 99
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Supply delivery & installation of various machineries at Alipurduar Division Office & allied Sub-Division Offices and laboratories under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000303/2021-2022 | 1287/ALD | 01/10/2021 | 16/10/2021 | MATRI ENTERPRISE | 1.75 | 1.75 | 100 | 97
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | CONSTRUCTION OF SLAB CULVERT OVER DRAIN INFRONT OF ALIPURDUAR PHED |  |  | ORD/000450/2018-2019 | 223/ALD | 26/02/2019 |  | AKANSHA COMMERCIAL PRIVATE LTD. | 0.52 | 3.84 | 732.72 | 0
Total | [13 empty] | 581.88 | 64.27 | 11.05