## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) | SM/07188 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000277/2021-2022 | 1844/ALD | 10/12/2021 | 09/01/2022 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.04 | 0 | 0 | 86.5
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) | SM/07188 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-3 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000280/2021-2022 | 1843/ALD | 10/12/2021 | 09/01/2022 | PROJIT HALDER | 5.02 | 2.18 | 43.45 | 87
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) | SM/07188 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BANCHUKAMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000315/2021-2022 | 2191/ALD | 11/01/2022 | 11/04/2022 | HITANGSHU CHOUDHURY | 21.92 | 19.14 | 87.32 | 56.33
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-2) | SM/07188 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Banchukamari PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000378/2021-2022 | 2378/ALD | 31/01/2022 | 01/04/2022 | SHIBA ENTERPRISE | 51.82 | 9.81 | 18.92 | 86.5
Total | [13 empty] | 83.8 | 31.12 | 37.14