## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVINATION OF 'JASHODANGA WATER SUPPLY SCHEME' | SM/09899 | Augmentation | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for JASHODANGA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000403/2021-2022 | 2394/ALD | 31/01/2022 | 01/05/2022 | MATRI ENTERPRISE | 24.02 | 17.8 | 74.11 | 44
2 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF 'JASHODANGA WATER SUPPLY SCHEME' | SM/09899 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Rejuvenation of Jashodanga Water Supply Scheme TW No.- IV under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000721/2022-2023 | 46/NMD-II | 04/01/2023 | 03/02/2023 | M/S KUNDU CONSTRUCTION | 4.31 | 4.22 | 97.95 | 100
3 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF 'JASHODANGA WATER SUPPLY SCHEME' | SM/09899 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Jashodanga Water Supply Scheme TW No.-III (Near Jashodanga Rural Hospital Premises) under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000778/2021-2022 | 167/NMD-II | 22/02/2022 | 24/03/2022 | BEE GEE CONSTRUCTION | 2.39 | 2.39 | 100 | 43
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF 'JASHODANGA WATER SUPPLY SCHEME' | SM/09899 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Jashodanga Water Supply Scheme TW No.-III (Near Jashodanga Rural Hospital Premises) under NMD-II,PHE Dte Alipurduar. | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000813/2021-2022 | 197/NMD-II | 24/02/2022 | 26/03/2022 | NABAUDYAG ELECTRICAL ENGINEERING CO- OPERATIVE SOCIETY LTD. | 7.74 | 7.71 | 99.62 | 44
5 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF 'JASHODANGA WATER SUPPLY SCHEME' | SM/09899 | Augmentation | Quotation for new service connection at Jasodanga W/SS TW No- III |  |  | VCH/001326/2022-2023 | BP-75/22-23 | 14/10/2022 |  | WBSEDCL | 1.23 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF 'JASHODANGA WATER SUPPLY SCHEME' | SM/09899 | Augmentation | Jashodanga W/S scheme T/W no. III, near Jashodanga Hospital campus |  |  | VCH/002697/2021-2022 | BP-40/21-22 | 26/03/2022 |  | WBSEDCL | 1.22 | 0 | 0 | 0
Total | [13 empty] | 40.91 | 32.12 | 78.53