## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' | SM/09901 | Augmentation | Laying of HDPE pipeline for Hantapara Topline under Hatapara WSS within Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000429/2021-2022 | 2627/ALD | 18/02/2022 | 19/04/2022 | DILIP MAHATO | 16.19 | 0 | 0 | 69
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' | SM/09901 | Augmentation | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for HANTUPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000433/2021-2022 | 2713/ALD | 23/02/2022 | 24/05/2022 | SUBIR GHOSH | 25.31 | 7.67 | 30.32 | 41
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' | SM/09901 | Augmentation | Laying of additional dedicated HDPE pipeline near PH No-1 village for the Hantapara WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000482/2021-2022 | 2904/ALD | 08/03/2022 | 07/05/2022 | SUBIR GHOSH | 11.78 | 8.03 | 68.13 | 39
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' | SM/09901 | Augmentation | Quotation for new service connection at Hantapara TW No- III |  |  | BILL/00040/2022-2023 | BP-129/22-23 | 13/01/2023 |  | WBSEDCL | 1.81 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' | SM/09901 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Hantapara T.G water supply scheme TW No. III under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000014/2022-2023 | 598/NMD-II | 05/05/2022 | 04/06/2022 | MIHIR SARKAR | 10.66 | 10.66 | 100 | 100
6 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HANTUPARA TG WATER SUPPLY SCHEME' | SM/09901 | Augmentation | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at Hantapara T.G Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000847/2022-2023 | 610/NMD-II | 20/03/2023 | 09/04/2023 | S.K ENTERPRISE | 3.3 | 3.3 | 100 | 100
Total | [13 empty] | 69.04 | 29.66 | 42.96