## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Providing FHTC from existing distribution system as per specification for JAGIJHORA PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000286/2023-2024 | 1993/ALD | 15/09/2023 | 14/11/2023 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 33.81 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Gap filling by DI and HDPE pipeline in Jagijhora Barabak PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000353/2023-2024 | 2605/ALD | 04/12/2023 | 31/07/2024 | MONORAMA ENTERPRISE | 9.99 | 2.6 | 26.07 | 25
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-2 Venue: 1) Jogijhora 2)Jateswar 3)Gopalpur 4)Madhya Parokata | HQ-A.E |  | ORD/000360/2021-2022 | 2122/ALD | 05/01/2022 | 04/02/2022 | MOYTEC | 4.9 | 4.9 | 100 | 26
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Construction of 300cum OHR for Augmentation of Jagijhora Barabak Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000414/2021-2022 | 2582/ALD | 17/02/2022 | 16/08/2022 | ASHIM KUMAR GHOSH | 63.76 | 29.65 | 46.5 | 42.5
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Construction of Pump House ,Boundary Wall and Tube well Boring by ODEX-165 Method of drilling including Rising Main for JAGIJHORA BARABAK PWSS under Alipurduar Division PHE DTE | Birpara A.E | Alipurduar Sub Division | ORD/000425/2021-2022 | 2609/ALD | 17/02/2022 | 18/05/2022 | SUBHAS CHANDRA ROY | 21.13 | 9.63 | 45.58 | 100
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Laying of distribution of HDPE/DI pipeline for Jogijhora Barabak PWSS under Alipurduar Division, PHE DTE. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000477/2021-2022 | 2896/ALD | 08/03/2022 | 06/07/2022 | MS DEYS CONSTRUCTION | 56.01 | 26.33 | 47.01 | 100
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Construction of boundary wall for Jogijhora Barabak PWSS of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/10169) | Birpara A.E | Birpara Sub Division | ORD/000509/2023-2024 | 827/ALD | 14/03/2024 | 13/05/2024 | MANI PRADHAN | 2.5 | 0 | 0 | 0
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Laying of HDPE pipe line for left out house hold connection at Ethelbari TG PWSS(SM/13449) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000540/2023-2024 | 894/ALD | 15/03/2024 | 13/06/2024 | DILIP MAHATO | 18.65 | 0 | 0 | 0
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Jogijhora WSS under Alipurduar Division, PHE Dte. Part-3 (2 nd call) | Birpara A.E | RWS Falakata Block | ORD/000572/2021-2022 | 3145/ALD | 25/03/2022 | 24/04/2022 | M/S SURAJIT DEY & CO | 5.02 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT JOGOJHORA BARABAK TW NO-III |  |  | BILL/00072/2023-2024 | BP-2023-24-66 | 13/05/2023 |  | WBSEDCL | 1.46 | 0 | 0 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Jogijhora Barabak water supply scheme, TW no. III under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000018/2023-2024 | 907/NMD-II | 04/05/2023 | 03/06/2023 | A.K SIKDAR | 10.36 | 5.04 | 48.68 | 100
Total | [13 empty] | 227.6 | 78.16 | 34.34