## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | SM/10678 | Augmentation | Laying of different dia DI,UPVC pipeline, bridge and culvert crossing and other works for providing FHTC at Jogendrapur and Satpukuri mouza at Augmentation of Jogendrapur PWSS under Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/10678) | Birpara A.E | Birpara Sub Division | ORD/000230/2024-2025 | 2283/ALD | 05/08/2024 | 04/10/2024 | MONORAMA ENTERPRISE | 21.88 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | SM/10678 | Augmentation | Laying distribution line, providing road and culvert crossing, and providing FHTC for Jogendrapur and Satpukuria Mouzas and adjacent areas, Cons. of Tubewell by ODEX-165 method of drilling, cons. of pump house and boundary wall for augmentation of JOGENDRAPUR PWSS. (2nd call) | Birpara A.E | Birpara Sub Division | ORD/000481/2022-2023 | 3198/ALD | 27/02/2023 | 26/08/2023 | BIJOY ROY | 159.61 | 45.76 | 28.67 | 25
3 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | SM/10678 | Augmentation | NEW SERVICE CONNECTION AT JOGENDRAPUR TW III |  |  | BILL/01972/2023-2024 | BP-2023-24-462 | 07/12/2023 |  | WBSEDCL | 5.36 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | SM/10678 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of JOGENDRAPUR water supply scheme, TW no III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000703/2023-2024 | 2144/NMD-II | 27/07/2023 | 26/08/2023 | BEE GEE CONSTRUCTION | 10.57 | 0 | 0 | 0
Total | [13 empty] | 197.42 | 45.76 | 23.18