## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | SM/11402 | Augmentation | Laying distribution system along with the other allied works at Santalabari under Augmentation of Jainti Wter Supply Scheme under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division |  | ORD/000209/2022-2023 | 1278/ALD | 17/08/2022 | 16/10/2022 | ASHOK SAPKOTA | 22.72 | 22.51 | 99.05 | 63
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | SM/11402 | Augmentation | Extension pipeline (HDPE) for providing FHTC at Santalbari area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000222/2021-2022 | 1619/ALD | 23/11/2021 | 22/01/2022 | M/S BHOWMICK CONSTRUCTION | 24.53 | 23.54 | 95.97 | 60.25
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | SM/11402 | Augmentation | Laying of HDPE pipeline for restoration of damaged pipeline and others allied works for Jainty WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000346/2022-2023 | 2490/ALD | 13/12/2022 | 12/01/2023 | TAPASH KUMAR BHOWMICK | 2.14 | 2.14 | 100 | 64
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | SM/11402 | Augmentation | Land development, construction of pathway of HWS and 2nd site of different sluice valve chamber and concrete blocks for MS pipe Jainti TG (Nimbu Dhora) WSS under Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000349/2022-2023 | 2491/ALD | 13/12/2022 | 11/02/2023 | DAS CONSTRUCTION | 9.41 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | SM/11402 | Augmentation | Laying of HDPE pipeline & other misc work related to Jayanti WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000354/2021-2022 | 2119/ALD | 05/01/2022 | 04/02/2022 | TAPASH KUMAR BHOWMICK | 4.28 | 0 | 0 | 71.25
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | SM/11402 | Augmentation | Balance work of Jainty Rest Shed along with laying of delivery line from CWR of Jainti WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000431/2021-2022 | 2629/ALD | 18/02/2022 | 19/04/2022 | GHOSH & SAHA CONSTRUCTION | 13.4 | 3.48 | 26.01 | 63.67
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | SM/11402 | Augmentation | Land development, construction of new pathway, surface drain (2nd site near Tea Factory) and other misc. works related to Jayanti TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000559/2022-2023 | 3503/ALD | 23/03/2023 | 22/05/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.39 | 0 | 0 | 0
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | SM/11402 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1261/ALD | 10/08/2023 |  | Resource Division | 7.92 | 0 | 0 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | SM/11402 | Augmentation | Complete elctrification of renovated existing Building Cum Rest Shed AT Jayanti W/S Scheme ,in the dist. Alipurduar. Under NMD-II, P.H E Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000029/2022-2023 | 627/NMD-II | 13/05/2022 | 12/06/2022 | ALPHA ENTERPRISE | 3.52 | 3.39 | 96.38 | 64
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JAYANTI PIPED WATER SUPPLY SCHEME | SM/11402 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Jayanti Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,,Apd. |  |  | ORD/001181/2023-2024 | 2913/NMD-II | 31/10/2023 | 30/11/2023 | MUSTAFI CONCERN | 12.17 | 0 | 0 | 0
Total | [13 empty] | 104.48 | 55.06 | 52.7