## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main, laying of DI and UPVC pipeline for Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000041/2023-2024 | 387/ALD | 19/05/2023 | 10/09/2024 | MITHUN DAS | 93.44 | 20.23 | 21.66 | 51
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Soil investigation at OHR site and construction of 450cum OHR at Uttar Sishubari under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000197/2024-2025 | 1767/ALD | 07/06/2024 | 03/04/2025 | BISWAJIT DUTTA | 118.67 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Construction of 450cum. OHR for Uttar Sishubari Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000259/2022-2023 | 1490/ALD | 05/09/2022 | 04/03/2023 | M/S DUTTA AND CO | 87.56 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. Part-4 | Birpara A.E | Alipurduar Sub Division | ORD/000260/2022-2023 | 1492/ALD | 05/09/2022 | 04/12/2022 | MITHUN DAS | 24.32 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Providing FHTC from existing distribution system as per specification for UTTAR SISHUBARI PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000284/2023-2024 | 1991/ALD | 15/09/2023 | 14/12/2023 | MITHUN DAS | 57.24 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Laying of distribution pipe in Uttar Sishubari Bazar area and Madarihat Bazar Area and allied works Under Birpara Sub-division, Alipurduar Division PHE DTE. | Birpara A.E |  | ORD/000396/2022-2023 | .2663/ALD | 22/12/2022 | 21/04/2023 | MITHUN DAS | 25.68 | 21.15 | 82.36 | 100
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Construction of Tubewell by ODEX-165 method of drilling at HWS, construction of pump house and boundary wall at HWS, laying of rising main for Aug. Of Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000473/2023-2024 | 691/ALD | 07/03/2024 | 21/04/2024 | MITHUN DAS | 31.88 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR UTTAR SISHUBARI MADARIHAT GOPAL BAGAN PWSS |  |  | BILL/00630/2024-2025 | BP-170/24-25 | 03/07/2024 |  | WBSEDCL | 5.41 | 0 | 0 | null
9 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR SISUBARI WATER SUPPLY SCHEME | SM/11959 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of UTTAR SISHUBARI Water Supply Scheme TWNo- I AND II under NMDII,PHE.Dte,APD. |  |  | ORD/001143/2023-2024 | 2887/NMD-II | 17/10/2023 | 16/11/2023 | S.D CONCERN WORKSHOP | 22.02 | 0 | 0 | 0
Total | [13 empty] | 466.23 | 41.39 | 8.88